List of Projects Submitted to DBM

Under NTA’s Irrigation Support Project for Small Tobacco Farmers (ISPSTFs)

| Location/Name of the Project |  | Approved Budget of the Contract | Fund Transferred | Fund Utilized | Unspent Balance (LGU) | Unreleased Balance (NTA) | REMARKS (% of Accomplish-ment) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| BATCH I |  |  |  |  |  |  |  |
| ABRA |  |  |  |  |  |  |  |
| Pilar |  |  |  |  |  |  |  |
| 1 | Construction of Sinanpenned SDD Brgy. Dintan. Pilar | 32,000,000 | 31,360,000 | 31,360,000 | - | - | 100% |
| Dolores |  |  |  |  |  |  |  |
| 2 | Construction of Namit-ingan SRIP – Namit-ingan, Dolores | 20,000,000 | 17,640,000 | 17,640,000 | - | 1,960,000 | 90% |
| Villaviciosa |  |  |  |  |  |  |  |
| 3 | Construction of Upper and Lower Gaong SRIP Lumaba, Villaviciosa | 15,000,000 | 14,700,000 | 14,700,000 | - | - | 100% |
| 4 | Rehabilitation of Laplapug SDD Laplapug, Villaviciosa | 5,000,000 | 4,900,000 | 4,900,000 | - | - | 100% |
| Tayum |  |  |  |  |  |  |  |
| 5 | Improvement of Budac SRIP Budac, Tayum | 3,000,000 | 2,940,000 | 2,940,000 | - | - | 100% |
| 6 | Construction of Sitio Wayya CIP Brgy. Velasco, Tayum, Abra | 8,000,000 | 7,840,000 | 7,836,129 | 3,871 | - | 100% |
|  |  | 83,000,000 | 79,380,000 | 79,376,129 | 3,871 | 1,960,000 |  |
| ILOCOS NORTE |  |  |  |  |  |  |  |
| Marcos |  |  |  |  |  |  |  |
| 7 | Rehabilitation & Improvement of Mabuti SIRP Mabuti, Marcos | 6,000,000 | 5,292,000 | 5,292,000 | - | 588,000 | 90% |
| Dingras |  |  |  |  |  |  |  |
| 8 | Construction of Capazan, SRIP Capasan, Dingras | 2,000,000 | 1,960,000 | 1,957,332 | 2,668 | - | 100% |
| 9 | Restoration of Bacsil SRIP Bacsil, Dingras | 3,000,000 | 2,940,000 | 2,937,755 | 2,245 | - | 100% |
| 10 | Construction of Upper, Middle and Lower Espiritu SRIP Dingras | 9,000,000 | 8,820,000 | 8,810,123 | 9,877 | - | 100% |
| Banna |  |  |  |  |  |  |  |
| 11 | Restoration of Barbarangay SRIP – Barbarangay, Banna | 2,000,000 | 1,960,000 | 1,960,000 | - | - | 100% |
| 12 | Restoration of Nagpatayan SRIP – Nagpatayan, Banna | 3,000,000 | 2,940,000 | 2,940,000 | - | - | 100% |
|  |  | 25,000,000 | 23,912,000 | 23,897,210 | 14,790 | 588,000 |  |
| ILOCOS SUR – I |  |  |  |  |  |  |  |
| Cabugao |  |  |  |  |  |  |  |
| 13 | Construction of Sitio Beckes-Arangan, Carusipan, Alinaay SRIP - Cabugao | 25,000,000 | 23,819,627 | 23,819,627 | - | 680,373 | 100% |
|  |  | 25,000,000 | 23,819,627 | 23,819,627 | - | 680,373 |  |
| Constructed by NTA |  |  |  |  |  |  |  |
| Sinait |  |  |  |  |  |  |  |
| 14 | Construction of Cabulalaan SRIP I - Cabulalaan, Sinait | 5,000,000 | - | 4,734,803 | - | 265,197 | 100% |
| 15 | Construction of Cabulalaan SRIP II - Cabulalaan, Sinait | 2,000,000 | - | 1,886,512 | - | 113,488 | 100% |
| 16 | Rehabilitation of Baracbac SRIP- Baracbac, Sinait | 5,000,000 | - | 4,781,840 | - | 218,160 | 100% |
| 17 | Expansion of Calingayan CIS Calingayan, Sinait | 1,000,000 | - | 941,656 | - | 58,344 | 100% |
|  |  | 13,000,000 | - | 12,344,811 | - | 655,189 |  |
| ILOCOS SUR - II |  |  |  |  |  |  |  |
| Burgos |  |  |  |  |  |  |  |
| 18 | Rehabilitation of Bessang SDD Bessang, Burgos | 5,000,000 | 4,900,000 | 4,900,000 | - | - | 100% |
| 19 | Rehabilitation of Balugang SDD Balugang, Burgos | 3,000,000 | 2,940,000 | 2,940,000 | - | - | 100% |
| San Emilio |  |  |  |  |  |  |  |
| 20 | Construction of Sitio Mangmanga, San Miliano, San Emilio | 5,000,000 | 4,900,000 | 4,896,895 | 3,105 | - | 100% |
| 21 | Rehabilitation of Kalumsing SDD Kalumsing San Emilio | 3,000,000 | 2,940,000 | 2,937,211 | 2,789 | - | 100% |
| Gregorio del Pilar |  |  |  |  |  |  |  |
| 22 | Construction of Badegna-Liswaaan Area SDD Gregorio del Pilar | 5,000,000 | 4,900,000 | 4,900,000 | - | - | 100% |
| 23 | Construction of Poblacion Sur SRIP Gregorio del Pilar | 3,000,000 | 2,940,000 | 2,940,000 | - | - | 100% |
| Lidlidda |  |  |  |  |  |  |  |
| 24 | Rehabilitation of Namatting SDD – Namatting, Poblacion Sur, Lilidda | 5,000,000 | 4,826,349 | 4,826,349 | - | 73,651 | 100% |
| 25 | Rehabilitation of Lidlidda-Turco SDD – Carcarabasa, Lidlidda | 5,000,000 | 4,900,000 | 4,897,313 | 2,687 | - | 100% |
| Salcedo |  |  |  |  |  |  |  |
| 26 | Construction of Dinaratan SRIP & SDD – Dinaratan, Salcedo | 22,000,000 | 21,457,866 | 21,457,866 | - | 102,134 | 100% |
| 27 | Improvement of Nagrebac, Nabucaan, Balidbid SDD. Salcedo | 12,000,000 | 11,685,887 | 11,685,887 | - | 74,113 | 100% |
| 28 | Improvement of Lucbuban SDD Lucbubab, Salcedo | 5,000,000 | 4,853,850 | 4,853,850 | - | 46,150 | 100% |
| Sta. Lucia |  |  |  |  |  |  |  |
| 29 | Rehabilitation of Banbanaba Alincoeg, Pila East SDD | 10,000,000 | 9,800,000 | 9,553,513 | 246,487 | - | 100% |
| Santiago |  |  |  |  |  |  |  |
| 30 | Construction of Salincub SRIP Salincub, Santiago | 20,000,000 | 19,558,830 | 19,558,830 | - | 41,170 | 100% |
| 31 | Construction of Al-aludig SRIP Al-aludig. Santiago | 20,000,000 | 17,640,000 | 17,640,000 | - | 1,960,000 | 90% |
| Suyo |  |  |  |  |  |  |  |
| 32 | Spring Development and Impounding Project-Mount Kin Listoquen-Cabugao | 5,000,000 | 4,900,000 | 4,900,000 | - | - | 100% |
| Nagbukel |  |  |  |  |  |  |  |
| 33 | Improvement of Mission SRIS (series of dams) Nagbukel | 5,000,000 | 4,900,000 | 4,810,986 | 89,014 | - | 100% |
| Narvacan |  |  |  |  |  |  |  |
| 34 | Rehabilitation of Upper and Lower Quinarayan, SDD Quinarayan | 12,000,000 | 11,760,000 | 11,760,000 | - | - | 100% |
| 35 | Rehabilitation of Casilagan SDD Casilagan, Narvacan | 3,000,000 | 2,940,000 | 2,940,000 | - | - | 100% |
| 36 | Rehabilitation of Upper and Lower Banglayan SDD - Banglayan | 12,000,000 | 11,760,000 | 11,760,000 | - | - | 100% |
| 37 | Restoration of Camarao SDD Camarao, Narvacan | 5,000,000 | 4,900,000 | 4,900,000 | - | - | 100% |
| 38 | Improvement of Sucoc SDD Sucoc, Narvacan | 2,500,000 | 2,450,000 | 2,450,000 | - | - | 100% |
| 39 | Improvement of Cadacad SDD Cadacad, Narvacan | 2,500,000 | 2,450,000 | 2,450,000 | - | - | 100% |
| 40 | Improvement of Marozo SDD, Marozo, Narvacan | 2,500,000 | 2,450,000 | 2,450,000 | - | - | 100% |
| Sta. Maria |  |  |  |  |  |  |  |
| 41 | Improvement of Gusing CIS Gusing Sta. Maria | 5,000,000 | 4,900,000 | 4,900,000 | - | - | 100% |
| Quirino |  |  |  |  |  |  |  |
| 42 | Construction of Bucnet SRIP Bucnet, Quirino | 3,000,000 | 2,940,000 | 2,930,948 | 9,052 | - | 100% |
| Cervantes |  |  |  |  |  |  |  |
| 43 | Construction of Libang SRIP Libang, Cervantes | 3,000,000 | 2,940,000 | 2,937,591 | 2,409 | - | 100% |
| Alilem |  |  |  |  |  |  |  |
| 44 | Restoration of Alilem Daya-Pump-Generated CIS | 5,000,000 | 4,900,000 | 4,887,380 | 12,620 | - | 100% |
| Sugpon |  |  |  |  |  |  |  |
| 45 | Rehabilitation and Improvement of Balbalayang SRIP Balblayang, Sugpon | 12,000,000 | 10,584,000 | 10,584,000 | - | 1,176,000 | 90% |
| Sta. Cruz |  |  |  |  |  |  |  |
| 46 | Rehabilitation of Cadaratan SDD Cadaratan, Sta. Cruz | 3,000,000 | 2,940,000 | 2,936,846 | 3,154 | - | 100% |
| 47 | Rehabilitation of Sitio Salasa SDD Pidpid, Sta. Cruz | 2,000,000 | 1,960,000 | 1,956,481 | 3,519 | - | 100% |
| Banayoyo |  |  |  |  |  |  |  |
| 48 | Rehabilitation of Tenga Elefante CIS – Tenga Elefante, Banayoyo | 2,000,000 | 1,960,000 | 1,957,953 | 2,047 | - | 100% |
| 49 | Improvement of Sitio Puspos CIS Puspos, Banayoyo | 3,000,000 | 2,940,000 | 2,937,192 | 2,808 | - | 100% |
| San Esteban |  |  |  |  |  |  |  |
| 50 | Rehabilitation of Sitio Mandulon Cabaroan CIS-Cabaroan San Esteban | 3,000,000 | 2,940,000 | 2,940,000 | - | - | 100% |
|  |  | 213,500,000 | 205,756,782 | 205,377,091 | 379,691 | 3,473,218 |  |
|  |  | 251,500,000 | 229,576,409 | 241,541,529 | 379,691 | 4,808,780 |  |
| LA UNION |  |  |  |  |  |  |  |
| Balaoan |  |  |  |  |  |  |  |
| 51 | Rehabilitation of Patpata Weste SRIP-Patpata Weste, Balaoan | 15,000,000 | 14,700,000 | 14,700,000 | - | - | 100% |
| 52 | Rehabilitation of Patpata Este SRIP-Patpata Este, Balaoan | 15,000,000 | 14,700,000 | 14,700,000 | - | - | 100% |
| 53 | Rehabilitation of Ar-arampang SRIS – Ar-arampang, Balaoan | 18,000,000 | 17,640,000 | 17,640,000 | - | - | 100% |
| 54 | Rehabilitation of Apaleng SRIS Apaleng, Balaoan | 15,000,000 | 14,700,000 | 14,700,000 | - | - | 100% |
| 55 | Rehabilitation of Ollaviano SRIS Sinapangan Sur, Balaoan | 12,000,000 | 11,760,000 | 11,760,000 | - | - | 100% |
| San Juan |  |  |  |  |  |  |  |
| 56 | Improvement of Pacapac- Bambanay SWIP Pacapac,San Juan | 3,000,000 | 2,843,318 | 2,843,318 | - | 96,682 | 100% |
|  |  | 78,000,000 | 76,343,318 | 76,343,318 | - | 96,682 |  |
|  | BATCH I | 437,500,000 | 409,211,727 | 421,158,186 | 398,352 | 7,453,462 |  |
| BATCH II |  |  |  |  |  |  |  |
| ABRA |  |  |  |  |  |  |  |
| San Quintin |  |  |  |  |  |  |  |
| 1 | Construction of Small Scale CIP Pantoc, San Quintin | 5,000,000 | 4,900,000 | 4,900,000 | - | - | 100% |
| 2 | Repair/Expansion of SSCIP Bingcong, Brgy. Villa Mercedes, San Quintin | 5,000,000 | 4,792,714 | 4,792,714 | - | 107,286 | 100% |
| 3 | Repair/Expansion of SSCIP Daput Falls Brgy. Pantoc to Villa Mercedes, San Quintin | 5,000,000 | 4,792,657 | 4,792,657 | - | 107,343 | 100% |
| Pidigan |  |  |  |  |  |  |  |
| 4 | Construction of SSCIP Brgy. San Diego, Pidigan | 7,000,000 | 6,174,000 | 6,174,000 | - | 686,000 | 90% |
| Tayum |  |  |  |  |  |  |  |
| 5 | Construction of CIP – (multi-barangays) | 20,000,000 | 19,593,513 | 19,593,513 | - | 6,487 | 100% |
| Peñarubia |  |  |  |  |  |  |  |
| 6 | Sta. Rosa Small Scale Water Impounding | 3,500,000 | 3,430,000 | 3,430,000 | - | - | 100% |
| 7 | Brgy Tattawa Small Scale Water Impounding | 2,000,000 | 1,960,000 | 1,960,000 | - | - | 100% |
| Luba |  |  |  |  |  |  |  |
| 8 | Expansion of Pusisit –Dadda-U CIS (Phase II) Upper Barit, Luba | 4,100,000 | 4,018,000 | 4,018,000 | - | - | 100% |
|  |  | 51,600,000 | 49,660,884 | 49,660,884 | - | 907,116 |  |
| ILOCOS NORTE |  |  |  |  |  |  |  |
| Pasuquin |  |  |  |  |  |  |  |
| 9 | Construction of Small SRIP- Brgy. Catalina | 25,000,000 | 24,500,000 | 24,500,000 | - | - | 100% |
| Banna |  |  |  |  |  |  |  |
| 10 | Construction of Lined Canal, Caribquib, Banna | 2,100,000 | 2,058,000 | 2,058,000 | - | - | 100% |
| 11 | Restoration of Bomitog SRIS,Bomitog, Banna | 2,500,000 | 2,450,000 | 2,450,000 | - | - | 100% |
| San Nicolas |  |  |  |  |  |  |  |
| 12 | Desilting/Dredging of Samac SWIP Brgy 17 Sta. Asuncion, San Nicolas | 3,600,000 | 3,175,200 | 3,175,200 | - | 352,800 | 90% |
| 13 | Desilting/Dredging of San Agustin SWIP Brgy 21 San Agustin, San Nicolas | 3,600,000 | 3,175,200 | 3,175,200 | - | 352,800 | 90% |
| 14 | Desilting/Dredging of Bingao SWIP Bingao, San Nicolas | 3,600,000 | 3,175,200 | 3,175,200 | - | 352,800 | 90% |
|  |  | 40,400,000 | 38,533,600 | 38,533,600 | - | 1,058,400 |  |
| Constructed by NTA |  |  |  |  |  |  |  |
| Solsona |  |  |  |  |  |  |  |
| 15 | Construction of Katangraran SWIP | 16,100,000 | - | 15,572,165 | - | 527,835 | 100% |
|  |  | 16,100,000 | - | 15,572,165 | - | 527,835 |  |
|  |  | 56,500,000 | 38,533,600 | 54,105,765 | - | 1,586,235 |  |
| ILOCOS SUR – I |  |  |  |  |  |  |  |
| San Juan |  |  |  |  |  |  |  |
| 16 | Construction of Tortorayok SWIP Muraya, San Juan | 5,000,000 | 735,000 | 735,000 | - | 4,165,000 | 15% |
| 17 | Construction of Tapao II SWIP Camanggaan, San Juan | 5,000,000 | 735,000 | 735,000 | - | 4,165,000 | 15% |
| 18 | Construction of Tapao III SWIP Camanggaan, San Juan | 5,000,000 | 735,000 | 735,000 | - | 4,165,000 | 15% |
| Nagbukel |  |  |  |  |  |  |  |
| 19 | Construction of Casilagan SWIP | 10,000,000 | 9,800,000 | 9,800,000 | - | - | 100% |
| San Emilio |  |  |  |  |  |  |  |
| 20 | Construction of Ken-Abara CIP Casilagan, Nagbukel | 9,000,000 | 8,820,000 | 8,820,000 | - | - | 100% |
| Gregorio del Pilar |  |  |  |  |  |  |  |
| 21 | Construction of Kenlunogan Bussot, Gregorio del Pilar | 3,000,000 | 2,940,000 | 2,940,000 | - | - | 100% |
| Sta. Cruz |  |  |  |  |  |  |  |
| 22 | Rehabilitation and Improvement of CAVILALA CIS – Calaoan Villa, Laurecia, Lantag | 10,000,000 | 9,795,236 | 9,795,236 | - | 4,764 | 100% |
| 23 | Repair and Rehabilitation of Padaoil CIS | 15,000,000 | 14,557,049 | 14,557,049 | - | 142,951 | 100% |
| Sta. Maria |  |  |  |  |  |  |  |
| 24 | Rehabilitation of Silag-Butir CIS | 3,000,000 | 2,791,380 | 2,791,380 | - | 148,620 | 100% |
| Quirino |  |  |  |  |  |  |  |
| 25 | Construction of Nabanew, Suagayan SWIP | 3,300,000 | 3,234,000 | 3,234,000 | - | - | 100% |
| 26 | Construction of Saoil-Poblacion SWIP | 3,300,000 | 3,234,000 | 3,234,000 | - | - | 100% |
| Cervantes |  |  |  |  |  |  |  |
| 27 | Rehabilitation of Pantar, San Juan CIS | 2,600,000 | 2,548,000 | 2,548,000 | - | - | 100% |
| Lidlidda |  |  |  |  |  |  |  |
| 28 | Construction of Anopol-Tapaan, Labut CIS | 5,000,000 | 4,900,000 | 4,900,000 | - | - | 100% |
| 29 | Construction of Batukal CIS | 5,000,000 | 4,900,000 | 4,900,000 | - | - | 100% |
| Sugpon |  |  |  |  |  |  |  |
| 30 | Construction of Brgy. Balbalayang, Suyo CIP | 4,500,000 | 3,969,000 | 3,969,000 | - | 441,000 | 90% |
| Banayoyo |  |  |  |  |  |  |  |
| 31 | Construction of Lintic CIP Brgy. Lintic | 10,000,000 | 8,820,000 | 8,820,000 | - | 980,000 | 90% |
| Narvacan |  |  |  |  |  |  |  |
| 32 | Rehabilitation of BantayAbot/Quinarayan SDD Brgy. Bantay Abot, Quinarayan | 10,000,000 | 9,638,300 | 9,638,300 | - | 161,700 | 100% |
| 33 | Rehabilitation of Marozo SDD Brgy. Marozo | 10,000,000 | 9,638,300 | 9,638,300 | - | 161,700 | 100% |
| 34 | Construction of Estancia SDD | 8,000,000 | 7,840,000 | 7,840,000 | - | - | 100% |
| 35 | Construction of Lanipao SDD | 5,000,000 | 4,500,000 | 4,500,000 | - | 400,000 | 100% |
| 36 | Construction of Cadacad SDD (Phase II) | 7,000,000 | 6,860,000 | 6,860,000 | - | - | 100% |
| Sto. Domingo |  |  |  |  |  |  |  |
| 37 | Construction/Rehabilitation of Irrigation Canal Brgys. Laoingen, Borobor, Calautit | 8,000,000 | 7,840,000 | 7,840,000 | - | - | 100% |
|  |  | 146,700,000 | 128,830,265 | 128,830,265 | - | 14,935,735 |  |
| LA UNION |  |  |  |  |  |  |  |
| Agoo |  |  |  |  |  |  |  |
| 38 | Construction of Capas CIS | 5,000,000 | 4,410,000 | 4,410,000 | - | 490,000 | 90% |
| 39 | Construction of Macalva Norte CIS | 5,100,000 | 4,495,260 | 4,495,260 | - | 502,740 | 90% |
| 40 | Construction of Macalva Sur | 4,200,000 | 3,704,400 | 3,704,400 | - | 411,600 | 90% |
| 41 | Construction of Ambitacay CIS | 7,700,000 | 6,786,922 | 6,786,922 | - | 759,078 | 90% |
| Bauang |  |  |  |  |  |  |  |
| 42 | Rehabilitation and Improvement of Palintucang CIS | 20,000,000 | 19,600,000 | 19,600,000 | - | - | 100% |
|  |  | 42,000,000 | 38,996,582 | 38,996,582 | - | 2,163,418 |  |
|  | BATCH II | 296,800,000 | 256,021,331 | 271,593,496 | - | 19,592,504 |  |
| BATCH III |  |  |  |  |  |  |  |
| ABRA |  |  |  |  |  |  |  |
| San Quintin |  |  |  |  |  |  |  |
| 1 | Construction of SSIP Kalaw, Zone 1, Brgy. Tangadan | 10,000,000 | 9,718,644 | 9,718,644 | - | 81,356 | 100% |
| Pidigan |  |  |  |  |  |  |  |
| 2 | Construction of Brgy. Yuyeng SSID/CIS | 10,000,000 | 1,470,000 | 1,470,000 | - | 8,330,000 | 15% |
| Bangued |  |  |  |  |  |  |  |
| 3 | Construction of Impounding Dam/Irrigation Canal Sagap CIS, Brgy Sitio Tina, Brgy. Sagap | 3,300,000 | 1,778,700 | 1,778,700 | - | 1,455,300 | 55% |
| Pilar |  |  |  |  |  |  |  |
| 4 | Construction of Brgy. Villavieja SDD | 20,000,000 | 19,600,000 | 19,600,000 | - | - | 100% |
| Villaviciosa |  |  |  |  |  |  |  |
| 5 | Construction of Lower Dungyasan CIS, Brgy. Laplapog | 9,100,000 | 8,900,000 | 8,900,000 | - | 18,000 | 100% |
| 6 | Rehabilitation of Denden- Patiao CIS, Brgy. Callao | 5,000,000 | 4,900,000 | 4,900,000 | - | - | 100% |
| 7 | Rehabilitation of Manmansanita CIS, Brgy. Poblacion | 5,000,000 | 4,900,000 | 4,900,000 | - | - | 100% |
| San Isidro |  |  |  |  |  |  |  |
| 8 | Construction of Brgy. Cabayugan SWIP | 10,000,000 | 9,800,000 | 9,800,000 | - | - | 100% |
| Peñarubia |  |  |  |  |  |  |  |
| 9 | Construction of Sitio Cabulatan/Malamsit Small Scale Irrigation Project | 2,300,000 | 2,254,000 | 2,254,000 | - | - | 100% |
|  |  | 74,700,000 | 63,321,344 | 63,321,344 | - | 9,884,656 |  |
| ILOCOS NORTE |  |  |  |  |  |  |  |
| Marcos |  |  |  |  |  |  |  |
| 10 | Rehabilitation and Improvement of SRIP Brgy. Imelda and Fortuna | 20,000,000 | 17,640,000 | 17,640,000 | - | 1,960,000 | 90% |
| Banna |  |  |  |  |  |  |  |
| 11 | Restoration of Irrigation Canal at Purok Minuri/SRIS | 2,100,000 | 2,058,000 | 2,058,000 | - | - | 100% |
| 12 | Restoration of Bangsar and Nagpatayan SRIP | 5,300,000 | 779,100 | 779,100 | - | 4,414,900 | 15% |
| Batac |  |  |  |  |  |  |  |
| 13 | Construction of San Pedro 3 Communal Irrigation System | 7,000,000 | 1,029,000 | 1,029,000 | - | 5,831,000 | 15% |
| San Nicolas |  |  |  |  |  |  |  |
| 14 | Construction of Establishment of SWIP, Sitio 2, Brgy. 20 San Pablo | 8,000,000 | 1,176,000 | 1,176,000 | - | 6,664,000 | 15% |
| Badoc |  |  |  |  |  |  |  |
| 15 | Construction of Zanjera Nagrebcan Water Impounding Brgy. Nagrebcan | 5,000,000 | 4,900,000 | 4,900,000 | - | - | 100% |
| Piddig |  |  |  |  |  |  |  |
| 16 | Construction/Rehabilitation of Tangaoan Communal Irrigation System | 6,000,000 | 5,880,000 | 5,880,000 | - | - | 100% |
| Pinili |  |  |  |  |  |  |  |
| 17 | Repair of Sanjera Pagdilao-Puritac Irrigation Canal Brgy. Puritac-Pagdilao | 10,000,000 | 9,800,000 | 9,800,000 | - | - | 100% |
|  |  | 63,400,000 | 43,262,100 | 43,262,100 | - | 18,869,900 |  |
| ILOCOS SUR |  |  |  |  |  |  |  |
| San Juan |  |  |  |  |  |  |  |
| 18 | Construction of Brgy. Cacandongan II SWIP | 5,000,000 | 735,000 | 735,000 | - | 4,165,000 | 15% |
| 19 | Construction of Brgy. Cacandongan I SWIP | 5,000,000 | 735,000 | 735,000 | - | 4,165,000 | 15% |
| 20 | Construction of Brgy. Dardarat SWIP | 5,000,000 | 735,000 | 735,000 | - | 4,165,000 | 15% |
| Cabugao |  |  |  |  |  |  |  |
| 21 | Construction of Caellayan SWIP | 5,000,000 | 4,900,000 | 4,900,000 | - | - | 100% |
| 22 | Construction of Bungro-Margaay SWIP | 2,700,000 | 2,646,000 | 2,646,000 | - | - | 100% |
| Magsingal |  |  |  |  |  |  |  |
| 23 | Rehabilitation of Patong SWIP | 10,000,000 | 9,800,000 | 9,800,000 | - | - | 100% |
| Nagbukel |  |  |  |  |  |  |  |
| 24 | Construction of Bandril SWIP | 10,000,000 | 9,800,000 | 9,800,000 | - | - | 100% |
| 25 | Construction of Small Water Impounding Project, Poblacion East | 10,000,000 | 9,800,000 | 9,800,000 | - | - | 100% |
| San Emilio |  |  |  |  |  |  |  |
| 26 | Construction of Boneg Communal Irrigation System, Brgy. Lancuas | 12,000,000 | 11,760,000 | 11,760,000 | - | - | 100% |
| Gregorio del Pilar |  |  |  |  |  |  |  |
| 27 | Construction of DECAA CIS, Brgy. Poblacion Norte | 3,000,000 | - | - | - | 3,000,000 | Unreleased fund |
| 28 | Construction of Lubnac CIS, Brgy. Dapdapog | 2,000,000 | - | - | - | 2,000,000 | Unreleased fund |
| Santa Cruz |  |  |  |  |  |  |  |
| 29 | Repair and Rehabilitation of DIMASAMA CIS Dili, Mambog, Sagat, Mantanas | 10,000,000 | 9,800,000 | 9,800,000 | - | - | 100% |
| 30 | Repair and Rehabilitation of CAUPLASAN CIS Amarao, San Pedro, Quinfermin | 10,000,000 | 9,800,000 | 9,800,000 | - | - | 100% |
| Candon |  |  |  |  |  |  |  |
| 31 | Construction of Langlangca, Bagar IS, Salvador II/Stone Lining Canal | 20,000,000 | 19,600,000 | 19,600,000 | - | - | 100% |
| 32 | Construction of Allangigan II CIS/Stone Lining Canal | 10,000,000 | 9,800,000 | 9,800,000 | - | - | 100% |
| 33 | Construction of Allangigan I CIS/Stone Lining Canal | 10,000,000 | 9,800,000 | 9,800,000 | - | - | 100% |
| Santa Maria |  |  |  |  |  |  |  |
| 34 | Construction of Brgy. Lubong WIP, Sta. Maria | 10,600,000 | 10,061,269 | 10,061,269 | - | 326,731 | 100% |
| Quirino |  |  |  |  |  |  |  |
| 35 | Construction of SWIP, Dagman Poblacion | 3,300,000 | 3,234,000 | 3,234,000 | - | - | 100% |
| 36 | Construction of SWIP, Airfield Madapoy, Ptungcaleo, Quirino | 3,300,000 | 3,234,000 | 3,234,000 | - | - | 100% |
| Alilem |  |  |  |  |  |  |  |
| 37 | Improvement of Amilongan CIS | 15,000,000 | 14,700,000 | 14,700,000 | - | - | 100% |
| Narvacan |  |  |  |  |  |  |  |
| 38 | Construction of Sarmingan Small Diversion Dam | 7,000,000 | 6,860,000 | 6,860,000 | - | - | 100% |
| 39 | Construction of Margaay-Bulanos Small Diversion Dam, Narvacan | 10,000,000 | 9,800,000 | 9,800,000 | - | - | 100% |
| 40 | Construction of Camarao Small Diversion Dam II, Narvacan | 10,000,000 | 9,800,000 | 9,800,000 | - | - | 100% |
| 41 | Construction of Banglayan Small Diversion Dam II, Narvacan | 10,000,000 | 9,800,000 | 9,800,000 | - | - | 100% |
| Lidlidda |  |  |  |  |  |  |  |
| 42 | Construction of TASABU Water Impounding Project, Labut | 10,000,000 | 9,799,652 | 9,799,652 | - | 348 | 100% |
| Sta. Lucia |  |  |  |  |  |  |  |
| 43 | Construction of Namatican/Nagtablaan CIS | 2,200,000 | - | - | - | 2,200,000 | Unreleased fund |
| Sugpon |  |  |  |  |  |  |  |
| 44 | Repair/Construction of Gayaman-Macabe Line Canal, Brgy. Balbalayang | 5,000,000 | 4,410,000 | 4,410,000 | - | 490,000 | 90% |
| Banayoyo |  |  |  |  |  |  |  |
| 45 | Construction of Barikir CIS, Brgy. Banbanaal | 5,000,000 | 4,900,000 | 4,900,000 | - | - | 100% |
| 46 | Construction of Ar-arangkin CIS, Brgy. Lopez | 5,000,000 | 4,900,000 | 4,900,000 | - | - | 100% |
| Galimuyod |  |  |  |  |  |  |  |
| 47 | Construction of Bosac Irrigation Dam/Canal Borobor, Sacaang and McKinley | 16,000,000 | 15,680,000 | 15,680,000 | - | - | 90% |
| Sigay |  |  |  |  |  |  |  |
| 48 | Construction of Malibuo, San Ramon SWID | 1,300,000 | - | - | - | 1,300,000 | Unreleased fund |
|  |  | 243,400,000 | 216,889,921 | 216,889,921 | - | 21,812,079 |  |
|  | BATCH III | 381,500,000 | 323,473,365 | 323,473,365 | - | 50,566,635 |  |
|  | GRAND TOTAL | 1,115,800,000 | 988,706,423 | 1,016,225,047 | 398,352 | 77,612,601 |  |

SDD – Small Diversion Dam     SRIP – Small Reservoir Irrigation Project     CIS – Communal Irrigation System

SWIP – Small Water Impounding Project     CIP – Communal Irrigation Project     SSIP – Small Scale Irrigation Project