PART II - OBSERVATIONS AND RECOMMENDATIONS

- FINANCIAL

- The Cash-Collecting Officers, Receivables, Other Current Assets and Other Non-Current Assets accounts aggregating P167.881 million representing 19.32 per cent of the total year-end balances of P868.853 million are not reliable, considering that these assets have been dormant for more than 10 to 29 years due to, among others: (a) undocumented balances of P97.235 million carried over from seven defunct tobacco agencies in 1987; (b) inclusion of unsettled loans of farmers/traders/ cooperatives since 1996 totaling P21.335 million with an interest of P15.265 million; (c) receivables from officers and employees no longer in the service in the total amount of P69,631; (d) unrecovered investment in bonds amounting to P28.634 million as the case of recovery had been dismissed by the court; and (e) non-provision of impairment loss on various dormant accounts.

  - This is an update of the observations contained in previous Annual Audit Reports (AARs) since recommendations to address the issues affecting the accounts were partially implemented.

  - As summarized in Table 1, the Cash-Collecting Officers, Receivables, Other Current Assets and Other Non-Current Assets accounts had total year-end balances of P1.105 billion, which included dormant balances for more than 10 to 29 years of P404.395 million or 36.58 per cent of the total balance. An allowance for impairment losses for Other Non-Current Assets amounting to P236.514 million was provided in calendar year (CY) 2017; thus, the total net balance amounted to P868.853 million.

Table 1 – Accounts with Dormant Balances

| Account | Total | 0 to 1 year | 1 to 5 years | 5 to 10 years | 10 to 29 years |
| --- | --- | --- | --- | --- | --- |
| Cash – collecting officers | P 654,888 | P 550,676 | P - | P - | P 104,212 |
|  | 654,888 | 550,676 | - | - | 104,212 |
| Receivables |  |  |  |  |  |
| Loans receivable-others | 637,646,723 | 248,764,574 | 279,014,776 | 88,532,278 | 21,335,095 |
| Interest receivable | 41,432,240 | - | - | 26,167,735 | 15,264,505 |
| Accounts receivable | 22,031,655 | 11,009,108 | 5,405,448 | 1,879,204 | 3,737,895 |
| Due from officers and employees | 3,516,480 | 830,300 | 2,039,050 | 577,499 | 69,631 |
| Inter-agency receivables | 17,514,544 | 46,654 | 16,516,983 | 78,525 | 872,382 |
| Other receivables | 50,396,552 | 947,229 | 12,037,135 | 6,452,876 | 30,959,312 |
|  | 772,538,194 | 261,597,865 | 315,013,392 | 123,688,117 | 72,238,820 |
| Other Current Assets |  |  |  |  |  |
| Prepayments – Other prepaid expenses | 4,893,155 | 27,706 | 13,417 | 1,300 | 4,850,732 |
| Advances – Disbursing officers | 1,658,734 | - | - | - | 1,658,734 |
| Other current deposits | 55,620 | - | - | - | 55,620 |
|  | 6,607,509 | 27,706 | 13,417 | 1,300 | 6,565,086 |
| Other Non-Current Assets (gross) | 325,566,615 | 40,000 | 31,795 | 8,037 | 325,486,783 |
|  | 325,566,615 | 40,000 | 31,795 | 8,037 | 325,486,783 |
| Gross | 1,105,367,206 | 262,216,247 | 315,058,604 | 123,697,454 | 404,394,901 |
| Less: Allowance for impairment losses (Other Non-Current Assets) | (236,513,922) | - | - | - | (236,513,922) |
| Net | P 868,853,284 | P 262,216,247 | P 315,058,604 | P 123,697,454 | P 167,880,979 |
| Percentage of Gross | 100 | 23.72 | 28.51 | 11.19 | 36.58 |
| Percentage of Net | 100 | 30.18 | 36.26 | 14.24 | 19.32 |

  - Under Item 5.4 of COA Circular No. 2016-005 dated December 19, 2016, on the Guidelines and Procedures on the Write-off of Dormant Receivable Accounts, Unliquidated Cash Advances and Fund Transfers of National Government Agencies (NGAs), Local Government Units (LGUs) and Government-Owned and Controlled Corporations (GOCCs), ‘Dormant Receivable Accounts’ is defined as: “accounts which balances remained inactive or non-moving in the books of accounts for ten (10) years or more and where settlement/collectability could no longer be ascertained.”

  - It is noteworthy to mention that Management submitted to the COA through the Audit Team its request for authority to write-off dormant accounts dated August 10, 2016, but the same was returned due to non-submission of the Death Certificates of deceased borrowers duly certified by the former National Statistics Office (NSO), now Philippine Statistics Authority (PSA).

Undocumented balances of P97.235 million carried over from seven defunct tobacco agencies in 1987

  - Under Executive Order (EO) No. 245, seven tobacco agencies were merged to the National Tobacco Administration (NTA), namely, Philippine Tobacco Administration (PTA); Philippine Virginia Tobacco Administration (PVTA); Philippine Virginia Tobacco Board (PVTB); Philippine Tobacco Research and Training Center (PTRTC); Virginia Tobacco Fuel Wood Corporation (VITOFCO); Virginia Flue-Curing Board (VFCB); and National Tobacco Classification Council (NTCC).

  - Verification disclosed that of the dormant accounts of P404.395 million (Table 1), P97.235 million or 24.04 per cent (Table 2) composed the balances carried over from the books of the seven defunct tobacco agencies consolidated to NTA in 1987.

Table 2 – Summary of Assets  - Balances from Seven Defunct Tobacco Agencies

|  | Amount |
| --- | --- |
| Accounts receivable | P 3,737,895 |
| Inter-agency receivables | 872,382 |
| Other current assets |  |
| Advances - Cash-disbursing officers | 1,658,734 |
| Prepayments – Other prepaid expenses | 4,850,732 |
| Other current deposits | 55,620 |
|  | 6,565,086 |
| Other non-current assets |  |
| Due from banks (DBP, LBP, PVB and PNB) | 70,292,538 |
| Loans receivable (irrigation pump, production loans and facility loans) | 7,192,940 |
| Contingent assets – tobacco shortages and miscellaneous | 6,070,861 |
| Unserviceable property | 2,492,286 |
| Other deposits | 10,738 |
| Other receivables – decided cases | 337 |
| Cash in bank – PVB – OGCC cash advance | 175 |
|  | 86,059,875 |
|  | P 97,235,238 |

DBP  - Development Bank  of the Philippines    LBP – Land Bank of the Philippines   PNB – Philippine National Bank

PVB – Philippine Veterans Bank       OGCC – Office of the Government Corporate Counsel

  - The dormant Accounts Receivable of P3.738 million comprised research and regulation fees of the seven defunct tobacco agencies, which were consolidated in the books by virtue of EO No. 116 dated January 30, 1987. Said accounts were no longer supported with complete documentation.

  - The Inter-agency Receivables of P0.872 million represents receivables from NGAs of the seven defunct tobacco agencies that were merged to the NTA.  These receivables were also not supported with documents.

  - The Other Current Assets – Advances - Disbursing Officers account of        P1.659 million consisted of unliquidated cash advances of former disbursing officers of the four defunct tobacco agencies, namely: PVTA, PTA, PVTB and VITOFCO which were no longer supported with documentation.

  - The Other Current Assets – Prepayments – Other prepaid  expenses totaling P4.851 million refer to undocumented prepayment balances in the books of the then PTRTC that were consolidated in the books of Batac Branch Office, which included mobilization expenses of P0.583 million incurred in the construction of the main NTA Building in Batac, Ilocos Norte; Letters of Credit (LCs) with PNB for various suppliers’ account of P3.489 million; and other prepaid expenses in the Central Office of        P0.779 million which include advance deposits to MERALCO of P0.521 million, Certeza Surveying and Aerophoto Systems, Inc. of P0.184 million for the relocation survey of the 94,802 square meters (sq. m.) of land owned by NTA in Las Piñas City, and Petrophil of P0.074 million. According to the Accountant, the transactions of the then PTRTC were consolidated in the books of Batac Branch Office without any documentation.

  - Out of the total of P86.060 million of Other Non-current Assets, only the Unserviceable Property account of P2.492 million was provided with allowance for depreciation amounting to P254,006.

Inclusion of unsettled loans of farmers/traders/cooperatives since 1996 totaling P21.335 million with an interest of P15.265 million

  - The pertinent provisions of Philippine Accounting Standard (PAS) No. 36 – Impairment of Assets provide as follows:

Paragraph 6: Xxx.  An impairment loss is the amount by which the carrying amount of an asset or a cash-generating unit exceeds its recoverable amount.

The recoverable amount of an asset or a cash-generating unit is the higher of its fair value less costs of disposal and its value in use.

Paragraph 8:  An asset is impaired when its carrying amount exceeds its recoverable amount.

Paragraph 9:  An entity shall assess at the end of each reporting period whether there is any indication that an asset may be impaired.  If any such indication exists, the entity shall estimate the recoverable amount of the asset.

Paragraph 12:  In assessing whether there is any indication that an asset may be impaired, an entity shall consider, as a minimum, the following indications:

External sources of information

- there are observable indications that the asset’s value has declined during the period significantly more than would be expected as a result of the passage of time or normal use.

- significant changes with an adverse effect on the entity have taken place during the period, or will take place in the near future, in the technological market, economic or legal environment in which the entity operates or in the market to which an asset is dedicated.

- Xxxx

- Xxxx

Paragraph 59-60:  If, and only if, the recoverable amount of an asset is less than its carrying amount, the carrying amount of the asset shall be reduced to its recoverable amount.  That reduction is an impairment loss.  An impairment loss shall be recognised immediately in profit or loss, unless the asset is carried at revalued amount in accordance with another Standard (for example, in accordance with the revaluation model in      IAS 16).  Xxx.

  - The dormant balance for 10 to 29 years of Loans Receivable-others amounting to P21.335 million (Table 1) pertains to unsettled loan balances of tobacco farmers and traders under the Facility/Production Assistance; Curing Barn Assistance and Tobacco Contract Growing System projects. The accrued interest thereon amounted to           P15.265 million. These loans remained unsettled because the farmer borrowers were either deceased or can no longer be located.

  - Verification revealed that NTA did not provide impairment loss on Loans Receivable and Interest Receivable, despite the collection thereof is already remote, if not nil.

Receivables from officers and employees no longer in the service in the total amount of P69,631

  - As regards the Due from Officers and Employees of P3.516 million (Table 1), the dormant account of P69,631 represents collectibles from officers and employees who are no longer connected with NTA.

Unrecovered investment in bonds amounting to P28.634 million as the case of recovery had been dismissed by the court

  - The Other Non-current Assets account of P325.567 million (gross)  includes Investment in Bonds  representing undelivered Land Bank of the Philippines (LBP) bond certificates of P28.634 million purchased in 1988 and 1989 from two private brokers/traders. A case had been filed against the former NTA Deputy Administrator for the possible recovery of the said bonds. However, the charges filed against her were dismissed by the Office of the Ombudsman in a Decision and Resolution dated November 2, 2011 and April 2, 2012, respectively, on the ground that the prescription period of 15 years to file a claim had already lapsed and the latter was no longer a public servant at the time the case was filed.  Thus, the recovery of the said bonds is      already nil.

Other Various Dormant Accounts

  - The details of the other dormant accounts shown in Table 1 are discussed in the succeeding paragraphs.

Undeposited collection of P104,212

  - The Cash-Collecting Officers account of P0.655 million includes undeposited collections of former collecting officers of the then PVTA and PTA totaling P104,212.

Dormant Other Receivables of P30.959 million

  - The dormant Other Receivables of P30.959 million included audit disallowances representing allowances and benefits of NTA officers and employees but were not yet settled, contrary to the provisions of COA Memorandum No. 2009-084 dated November 16, 2009, on the Enforcement of COA Disallowances and Charges, which provides for the settlement of disallowances and charges which have become final and executory.

  - Dormant Other Receivables also included P3.923 million that pertained to the accounts of 24 employees who were awarded lots in Tuguegarao, Cagayan pursuant to Resolution Nos. 110-94 dated February 22, 1994 and 216-94 dated October 5, 1994. There were no payments made by the said employees notwithstanding actual possession and use of the land as well as acquisition of land titles in their respects or their successors. Twelve recipients have already sold their lots to third parties without settling of their accounts.

Dormant Other Non-current Assets

  - Of the total dormant accounts under Other Non-current Assets of           P325.487 million, NTA provided Allowance for Impairment Losses and Depreciation aggregating P236.514 million.

  - The dormant Other Non-current Assets included reforestration projects of       P0.616 million jointly implemented by the NTA and the Department of Environment and Natural Resources (DENR) in 1993 to 1996 with two cooperatives in Ilocos Sur and one in Ilocos Norte.  These projects were covered by a Memorandum of Agreement (MOA).  Reports disclosed that the cooperatives no longer exist and the projects have been abandoned though the trees with recoverable value still exist in the project site in Vigan, Ilocos Sur.

  - Although Management has partially complied with last year’s audit recommendations such as sending of at least three collection/demand letters to clients, and memoranda to concerned Branch Managers on the issues relative to Other Current Assets that were still outstanding in their books, they have not requested for authority to write-off these accounts from COA. Also, updates on further action to be undertaken were not submitted to the Audit Team as at audit date.

  - In view of the foregoing observations, the Cash-Collecting Officers, Receivables, Other Current Assets and Other Non-Current Assets accounts are not reliable.

  - We reiterated our previous years’ recommendations that Management instruct:

- The Central/Regional Offices’ Accountants to:

a.1 	Complete the documentation of dormant accounts aged 10 to 29 years in accordance with COA Circular No. 2016-05 dated December 19, 2016 to support the request for authority to write off from COA;

a.2 	Exert utmost  efforts to retrieve/recover any documents and verify the undeposited collection and unliquidated Cash Advances of the former Cash Collecting and Disbursing Officers, respectively of the four defunct tobacco agencies;

a.3 	Enforce immediate settlement of unliquidated cash advances and receivables from officers and employees by filing collection cases if claims remained uncollected even after sending demand letters;

a.4 	Analyze the Other Current Assets accounts and prepare the necessary adjustments in the books; and

- The Legal Officer to:

b.1 	Determine the probability of redemption of the bonds amounting to P28.634 million included in Other Non-current Assets account, and if the recovery is already nil, complete the documents for write-off of the account for filing with the COA;

b.2 	Exert all legal remedies for the rescission of the Certificates of Award and for the reconveyance of the pertinent lots located in Tuguegarao, Cagayan to the government pursuant to Resolution      No. 258-2012 dated April 12, 2012 of the NTA Governing Board, if the awardees and/or the occupants/possessors/successors of the           24 unpaid lots included in Other Receivables of P3.923 million do not agree to settle in full the cost with increments; and

c.	The concerned Branch Managers to make representations with the DENR for the possible transfer of the reforestation project sites included in Other Current Assets account to the local government units so as to preserve the area.

  - We further recommended that Management provide impairment loss on dormant assets pursuant to PAS No. 36.

  - Management informed during the Exit Conference on April 25, 2018 that the request for authority to write-off Trade Receivables from Tobacco Centers (TCs) in Region I in the amount of P0.788 million was granted under COA-NTA Decision           No. 2017-01 dated October 26, 2017, while collection letters were sent in November 2017 to eight TCs with balance of P95,803.

  - Also, Management commented that:

- A Certification from the Securities and Exchange Commission (SEC) that the Certificates of Registration of the two  private brokers/traders, that purchased the LBP bond certificates of P28.634 million in behalf of  NTA, were revoked on September 29, 2003;

- Some of the awardees of the unpaid lots located in Tuguegarao, Cagayan, are paying monthly amortization to their respective Branch Offices. A new Attorney V was hired to file cases against those who still do not pay.

- With regard to the issue on reforestation project sites to be transferred to the LGUs, NTA is still awaiting actions from DENR for the permit or authority to cut trees under their supervision.

  - As a rejoinder, the Audit Team acknowledged the initial efforts undertaken by Management to implement the recommendations.  However, their full compliance with all the above-mentioned recommendations will be monitored in CY 2018.

- The existence and completeness of the Property, Plant and Equipment (PPE) account with total cost of P702.433 million as at December 31, 2017 could not be ascertained due to: (a) incomplete physical inventory of immovable assets in NTA–Central Office (CO) totaling P120.819 million; (b) discrepancies of P170.458 million between accounting records of P165.331 million and property records of P335.789 million in NTA–CO and Isabela Branch; (c) non-provision of allowance for impairment loss on the idle property in NTA Cagayan Branch which is not in accordance with Philippine Public Sector Accounting Standards (PPSAS) 21; and (d) other deficiencies which affect the ownership of NTA over                      its properties.

  - This is a reiteration with updates of the prior year’s observations as Management was unable to implement fully all the audit recommendations.

  - As at December 31, 2017, the PPE account had a total cost of P702.433 million and carrying value of P465.327 million as shown itemized in Table 3.

Table 3 – Composition of PPE Account as at December 31, 2017

| PPE Account | Cost | Accumulated Depreciation | Carrying Value |
| --- | --- | --- | --- |
| Land, land improvements, buildings and other structures | P 457,812,854 | P 106,359,595 | P 351,453,259 |
| Various equipment | 206,530,725 | 105,223,096 | 101,307,629 |
| Furniture and fixtures, books, motor vehicles and other PPE | 38,089,298 | 25,523,591 | 12,565,707 |
| Construction in progress | - | - | - |
|  | P 702,432,877 | P 237,106,282 | P 465,326,595 |

  - Section 38 of the Government Accounting Manual (GAM) for National Government Agencies, Volume II, states:

Physical Count of PPE. The entity shall have a periodic physical count of PPE, which shall be done annually and presented on the Report on the Physical Count of Property, Plant and Equipment (RPCPPE) as at December 31 of each year. This shall be submitted to the Auditor concerned not later than January 31 of the following year. Equipment found at station and losses discovered during the physical count shall be reported to the Accounting Division/Unit for proper accounting/recording.

  - Under the same Section of GAM, physical inventory taking is an indispensable procedure to check the existence and condition of the assets.

  - Likewise, Chapter 10, Section 42 of the GAM states that:

Report on the Physical Count of Property, Plant and Equipment (RPCPPE) is the form used to report on the physical count of PPE by type such as land, land improvement, infrastructure, building and other structures, machinery and equipment, transportation equipment, furniture, fixtures and books, etc. which are owned by the agency. It shall be prepared yearly by fund cluster as of a given date. It shows the balance of property and equipment per cards and per count and shortage/overage,    if any.

  - The RPCPPE shall be certified correct by the Inventory Committee Chair and Members, approved by the Head of the Agency/Entity, verified by the COA representative and shall be submitted to the Auditor concerned and Accounting Division/Unit not later than January 31 of each year.

  - It is worth mentioning that Management created an Inventory Committee in the CO to conduct the physical inventory of its PPE costing P214.809 million on December 20, 2017 under Special Order No. 1044 s. 2017 dated December 4, 2017 and it submitted to the Audit Team the required RPCPPE on January 31, 2018.

  - Nevertheless, audit of PPE account with total cost of P702.433 million as at December 31, 2017 disclosed similar deficiencies noted  in previous years’ audits which are discussed  in the succeeding paragraphs:

Incomplete physical inventory of immovable assets in NTA–CO totaling P120.819 million

  - Physical Inventory of immovable assets valued at P120.819 million was partially conducted for CY 2017. On August 16, 2017, a Team composed of representatives from the Property and Accounting Divisions of NTA together with representatives from       COA-NTA conducted an ocular inspection of immovable properties located in Panay Avenue, Quezon City; Paco, Manila; Las Piñas City; and Rodriguez, Rizal. However, other immovable properties recorded in the books of NTA-CO and located in the Cordillera Administrative Region (CAR), Regions I and II were not inspected; thus, the completeness and existence of the immovable assets valued at P120.819 million were not ascertained as at year-end.

Discrepancies of P170.458 million between accounting records of P165.331 million and property records of P335.789 million in NTA–CO and Isabela Branch

  - Comparison of PPE between Accounting and Property Records disclosed discrepancies aggregating P170.458 million, as presented in Table 4.

Table 4 – Comparison of PPE between Accounting and Property Records

(Head Office and Isabela Branch)

| PPE Account | Accounting Records | Property Records | Discrepancy |
| --- | --- | --- | --- |
| NTA- CO |  |  |  |
| Land | 47,439,584 | 252,981,908 | (205,542,324) |
| Land improvements | 572,528 | - | 572,528 |
| Buildings | 72,786,570 | 40,483,913 | 32,302,657 |
| Other structures (visitors’ quarters) | 20,400 | - | 20,400 |
| Total Immovable Assets | 120,819,082 | 293,465,821 | (172,646,739) |
| Office equipment | 881,855 | 854,355 | 27,500 |
| Motor vehicles | 14,378,845 | 13,379,295 | 999,550 |
| NTA – Isabela Branch | 29,251,110 | 28,089,883 | 1,161,227 |
|  | 165,330,892 | 335,789,354 | (170,458,462) |

  - Discrepancies noted were due to the following:

- The discrepancy of P205.542 million on Land account was due to the value of claimed parcels of land by NTA based on the zonal values which were included in the RPCPPE. These parcels of land located in the Mountain Province, Apayao and Cagayan were properties of the seven (7) defunct tobacco agencies merged to NTA, which were not yet recorded in the books of accounts since the Transfer Certificate of Titles (TCTs) are not yet in the name of NTA. These lands remained idle and others are now occupied by illegal settlers; hence, depriving the Agency of whatever income and benefits that could be derived therefrom; exposing the Agency to possible risk of losing the property; and this might pose difficulty in claiming these properties from third parties. In NTA-Isabela Branch, the RPCPPE was not submitted and there was a discrepancy amounting to P1.161 million between accounting records of P29.251 million and property records of P28.090 million.

- Land Improvements pertain to improvements made in Golden Leaf Village located in Brgy. San Isidro, Rodriguez, Rizal for the concrete wall and water system as well as the motorpool fence in NTA CO, that were completed on April 14, 2010, December 19, 2012 and October 10, 2014, respectively. The Other Structures pertain to the scaffoldings used in the renovation/repair of visitors’ quarters amounting to P20,400 which were completed on January 26, 2016 but were not included in the RPCPPE.

- The breakdown of the discrepancy noted in the Buildings account is presented in Table 5.

Table 5 – Discrepancy on Buildings account between Accounting and Property Records

| Description | Amount |  | Discrepancy |
| --- | --- | --- | --- |
|  | Accounting Records | Property Records |  |
| NTA Building | P 47,846,430 | P 17,250,000 | P 30,596,430 |
| Quality Assurance Building (laboratory) | 16,314,315 | 19,676,730 | (3,362,415) |
| Building (COA) | 2,799,668 | 1,400,000 | 1,399,668 |
| Building (motorpool) | 2,079,934 | 1,300,000 | 779,934 |
| Employees Quarters | 1,245,800 | 857,183 | 388,617 |
| Unaccounted properties from the 7 defunct tobacco agencies merged to NTA | 2,500,423 | - | 2,500,423 |
|  | P 72,786,570 | P 40,483,913 | P 32,302,657 |

c.1 	The discrepancy of P32.303 million on Buildings account represents retrofitting, several renovations (Offices, Comfort Room, electrical and pipes/tanks), repainting, rehabilitation of roofing, drainage system and Installation of Feeder Lines (Rider) which were not included in the Property Division Records.

c.2 	There were unaccounted properties amounting to P2.500 million from the seven  defunct tobacco agencies merged to NTA which are recorded in the books.

c.3 	The Property Division recorded the Quality Assurance Building in the full contract price of P19.677 million, while the Accounting Division recorded only P16.314 million or 83 per cent, since it was not yet turned-over to NTA upon completion and the Contractor had not yet claimed the             remaining amount.

- The digital camera amounting to P27,500 under the Office Equipment account was from the Multi-Line Food Processing Plant (MFPP) project that was not included in the RPCPPE since until now the Supply Officer could not identify the end-user.

- Moreover, NTA purchased three motor vehicles in CY 2017 which were recorded during the year. However, one motor vehicle amounting to P999,550 remained undelivered as at year-end, thus not included in the RPCPPE.

- One Motor vehicle, Isuzu Crosswind (Plate No. MVH-040) amounting to P830,000 was transferred without cost to the Department of Agriculture (DA),  but remained recorded both in the accounting and property records, thus, overstating the PPE account.

Non-provision of allowance for impairment loss on the idle property in NTA Cagayan Branch which is not in accordance with PPSAS 21

  - Paragraph 23 of PPSAS 21 states:

This standard defines an impairment as a loss in the future economic benefits or service potential of an asset, over and above the systematic recognition of the loss of the asset’s future economic benefits or service potential through depreciation (amortization). Impairment, therefore, reflects a decline in the utility of an asset to the entity that controls it. For example, an entity may have a purpose-built military storage facility that it no longer uses. In addition, because of the specialized nature of the facility and its location, it is unlikely that it can be leased out or sold, and therefore the entity is unable to generate cash flows from leasing or disposing of the asset. The asset is regarded as impaired, as it is no longer capable of providing the entity with service potential – it has little, or no, utility for the entity in contributing to the achievement of its objectives. [Emphasis supplied]

  - In NTA Cagayan Branch, the warehouse building costing P120,740 remained idle for years and was not subjected for impairment testing as required under PPSAS 21 governing the Impairment of Non-Cash Generating Assets.

  - An idle asset incurs operating expenses for its maintenance, while the Agency was deprived of any return from economic ventures with the use of this government property such as the rental of the asset for commercial or agricultural use. Since this idle asset was no longer used by the Agency, this might be impaired; hence affecting the fair valuation of the PPE in the financial statements.

Other deficiencies which affect the ownership of NTA over its properties

  - A considerable portion of the parcels of land consisting of 25,017 square meters costing P14.760 million, where the NTA Isabela Branch Office Building is erected, is being occupied by informal settlers. These parcels of land were recorded in the books, but remained not titled in the name of NTA. Under Proclamation No. 454 dated September 19, 1939 by then President Manuel L. Quezon, these lots were reserved for warehousing purposes. According to the Administrative Officer, the informal settlers, who have been occupying the area since 1980, were former employees of the Philippine Tobacco Administration (PTA).

  - Seven parcels of agricultural land in Isabela Branch used for tobacco research and development with an aggregate area of 66,264 square meters in the name of PTA, which were transferred to NTA pursuant to EO No. 245, were not recognized in the books. These parcels of land were also the subject of Department of Agrarian Reform (DAR) Emancipation Patents (EPs) in favor of DAR beneficiaries. The issuance of EPs relative thereto was questionable because the properties were titled in the name of PTA (now NTA) and transfers of title thereof were made without the consent of NTA. The Administrative Officer presented a letter-complaint filed against the DAR by the NTA Administrator dated September 28, 2017, requesting for validation of the matter and for the consequent cancellation of the said EPs.

  - Land costing P153,453 where NTA La Union Branch is situated, and 115 parcels of land owned by NTA Batac Branch costing P2.627 million were not supported with Transfer Certificates of Title (TCTs) and other legal documents of ownership, thus affecting the Agency’s claim and rights of ownership over the          said properties.

  - The land where the NTA Batac Branch building stands and where some of its facilities were located was not recorded in the books of the Agency. The land is owned by the Mariano Marcos State University (MMSU), creating uncertainty on the rights and ownership of NTA over said building and facilities.

  - Two NTA Ilocos Norte Branch buildings with total book value of P1.708 million were donated to Isabela State University (ISU) but still included in the books; hence, overstating the PPE account by the same amount. The properties were not derecognized from the books as the NTA CO has not forwarded a copy of the Deed of Donation in favor of ISU, which would serve as basis of the Branch Accountant to drop the same from the books.

  - A parcel of land located in Cabanatuan City was recorded in the books of NTA Pangasinan Branch in the amount of P150,000, but it was found not owned by the Agency as the donation from the National Food Authority (NFA) did not materialize. Management informed that they will drop from the books said lot, since it is not duly owned by the Agency.

  - As a result of the aforementioned deficiencies, the existence and completeness of the PPE account with total cost of P702.433 million as at December 31, 2017 could not be ascertained.  Likewise, the ownership of NTA over some properties recorded in the books could not be established due to absence of documents and records.

  - We recommended and Management agreed to:

  - Require the Inventory Committee to complete the conduct of physical inventory of immovable assets in NTA-CO books including the properties located in CAR, Regions I and II to check their existence and conditions and, to prepare the RPCPPE for reconciliation with the accounting and property records and to identify the missing and unrecorded properties in the books;

  - Conduct periodic reconciliation of the records between accounting and property records of CO and Isabela Branch after physical inventory taking and effect the necessary adjustments in the books, if any;

  - Conduct impairment testing of the idle property in NTA Cagayan Branch to determine the amount of allowance to be provided;

  - Undertake necessary actions/measures for the removal of the informal settlers in all NTA properties to be used for warehousing purposes as provided under Proclamation No. 454 dated September 19, 1939 by then President Manuel L. Quezon;

  - Exhaust all remedies for the recovery of parcels of land in Isabela subject of EPs in favor of DAR beneficiaries and, follow up reply of DAR on letter-complaint filed by the NTA for the consequent cancellation                of the EPs;

  - Require the person responsible  in the CO to provide NTA Batac Branch copy of the Deed of Donation of the two buildings donated to ISU in order for the Branch Accountant to drop these properties from the books;

  - Exhaust all possible means to facilitate the preparation of documentary requirements to secure the TCTs of all parcels of land acquired, as evidence of ownership of NTA over these properties;

  - Require the Accountant of NTA Pangasinan Branch to drop the parcel of NFA land recorded in the books as the donation did not materialize; and

  - Instruct the Accountant of NTA-CO to drop from the books the motor vehicle transferred without cost to the DA.

  - Management commented that:

- One of the Directors of the Governing Board took the lead in the inventory of NTA real/immovable properties;

- They had already hired personnel assigned to gather documents such as Tax Declarations for the proper valuation and establish the ownership of NTA properties;

- In Batac Branch, an Officer-in-Charge of all properties especially those immovable assets was designated to establish their correctness and reconcile with the Finance Department for the tax declaration as basis for recording          in the books;

- As of now, the claim from the Board of Liquidators amounting to         P0.800 million as payment for the lots occupied by the DA in Cagayan is in progress; and

- In Ilocos Norte Branch, they have located the MOA between NTA and MMSU on the exchange of lots and committed to take effect all the agreements stipulated in the contract.

  - As a rejoinder, the Audit Team would monitor Agency’s compliance with the recommendations in CY 2018.

- COMPLIANCE

Irrigation Support Project for Small Tobacco Farmers (ISPSTFs)

- NTA undertook the overall supervision of the implementation of                137 irrigation projects of 79 Local Government Units (LGUs) in the Cordillera Administrative Region (CAR) and Region I aggregating P969.596 million, and direct implementation of four projects in Sinait, Ilocos Sur and one project in Solsona, Ilocos Norte totaling P27.917 million, or a total of P997.513 million in    CYs 2014-2017 which were not in consonance with its mandate as provided under EO No. 245. Furthermore, deficiencies were noted in the implementation of the ISPSTFs which included, among others: (a) non-submission of certifications of NTA Accountant that funds amounting to P969.596 million previously transferred to the LGUs as implementing agencies have been liquidated and accounted for in the books; (b) non-settlement/liquidation of funds transferred to 35 LGUs totaling P113.090 million despite project completion; (c) unutilized portion of funds totaling P398,354 were not refunded to NTA by 11 LGUs contrary to Item 4.9 of COA Circular No. 94-013; and (d) a total of P3.669 million excess funds remained under the custody of NTA and were not reverted back to the Bureau of Treasury.

  - The Department of Budget and Management (DBM) released the allotted funds of P437.500 million, P296.800 million and P381.500 million for 56 irrigation projects in Batch I (CY 2014), 42 projects in Batch II (CY 2015), and 48 projects in Batch III        (CY 2016), respectively, or a total of P1,115.800 million for the implementation of NTA’s ISPSTFs from CYs 2015 - 2017. Of the total funds received from DBM, P1,065.136 million (net of two per cent supervision fee) was allocated to Municipalities in CAR and Region I for the construction and repair/rehabilitation/restoration/improvement/ development/expansion of 146 identified irrigation systems.

  - The DBM-approved irrigation projects under Batches I, II and III, are summarized in Table 6, with details shown in Annexes A and B of this Report.

Table 6 – Summary of ISPSTFs Approved Budget, Fund Allocations,

Fund Transferred and Balances as of December 31, 2017

| Location |  |  | No. of LGUs | No of Projects | Approved Budget Cost | Project Cost Allocated to LGUs | Funds Transferred to LGUs | Fund Utilized | Balance |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| BATCH I |  |  |  |  |  |  |  |  |  |
| Abra |  |  | 4 | 6 | 83,000,000 | 81,340,000 | 79,380,000 | 79,376,129 | 1,960,000 |
|  |  | Ilocos Norte | 3 | 6 | 25,000,000 | 24,500,000 | 23,912,000 | 23,897,210 | 588,000 |
|  |  | Ilocos Sur | 19 | 34 | 238,500,000 | 233,730,000 | 229,576,409 | 229,196,718 | 4,153,591 |
|  |  | La Union | 2 | 6 | 78,000,000 | 76,440,000 | 76,343,318 | 76,343,318 | 96,682 |
|  |  |  | 28 | 52 | 424,500,000 | 416,010,000 | 409,211,727 | 408,813,375 | 6,798,273 |
| BATCH II |  |  |  |  |  |  |  |  |  |
|  |  | Abra | 5 | 8 | 51,600,000 | 50,568,000 | 48,680,884 | 48,680,884 | 1,887,116 |
|  |  | Ilocos Norte | 3 | 6 | 40,400,000 | 39,592,000 | 38,533,600 | 38,533,600 | 1,058,400 |
|  |  | Ilocos Sur | 13 | 22 | 146,700,000 | 143,766,000 | 122,656,265 | 111,876,265 | 21,109,735 |
|  |  | La Union | 2 | 5 | 42,000,000 | 41,160,000 | 38,996,582 | 38,996,582 | 2,163,418 |
|  |  |  | 23 | 41 | 280,700,000 | 275,086,000 | 248,867,331 | 238,087,331 | 26,218,669 |
| BATCH III |  |  |  |  |  |  |  |  |  |
|  |  | Abra | 7 | 9 | 74,700,000 | 73,206,000 | 58,911,344 | 58,911,344 | 14,294,656 |
|  |  | Ilocos Norte | 7 | 8 | 63,400,000 | 62,132,000 | 38,264,100 | 38,264,100 | 23,867,900 |
|  |  | Ilocos Sur | 14 | 27 | 234,900,000 | 230,202,000 | 214,341,921 | 214,341,921 | 15,860,079 |
|  |  |  | 28 | 44 | 373,000,000 | 365,540,000 | 311,517,365 | 311,517,365 | 54,022,635 |
| Constructed by NTA BATCH I - Ilocos Sur |  |  | 1 | 4 | 13,000,000 | - | - | 12,344,811 | 655,189 |
| BATCH II- Ilocos Norte |  |  | 1 | 1 | 16,100,000 | - | - | 15,572,165 | 527,835 |
|  |  |  | 2 | 5 | 29,100,000 | - | - | 27,916,976 | 1,183,024 |
| Projects not yet implemented |  |  |  |  |  |  |  |  |  |
| BATCH III - Ilocos Sur |  |  | 3 | 4 | 8,500,000 | 8,500,000 | - | - | 8,500,000* |
|  |  |  | 3 | 4 | 8,500,000 | 8,500,000 |  | - | 8,500,000 |
|  |  |  | 84 | 146 | 1,115,800,000 | 1,065,136,000 | 969,596,423 | 986,335,047 | 96,722,601 |
| Total Projects |  |  |  |  |  |  |  |  |  |
| Batch I |  |  | 29 | 56 | 437,500,000 | 416,010,000 | 409,211,727 | 421,158,186 | 7,453,462 |
| Batch II |  |  | 24 | 42 | 296,800,000 | 275,086,000 | 248,867,331 | 253,659,496 | 26,746,504 |
| Batch III |  |  | 31 | 48 | 381,500,000 | 374,040,000 | 311,517,365 | 311,517,365 | 62,522,635 |
|  |  |  | 84 | 146 | 1,115,800,000 | 1,065,136,000 | 969,596,423 | 986,335,047 | 96,722,601 |

  - As of December 31, 2017, a total of P969.596 million was transferred to 79 LGUs from the allocated funds of P1,115.800 million. Of the 146 projects under Batches I to III, four were implemented by the NTA in the Municipality of Sinait, Ilocos Sur under Batch I and one in the Municipality of Solsona, Ilocos Norte under Batch II, while four projects were not yet implemented as of December 31, 2017 under Batch III.

Overall supervision of NTA in the Implementation of ISPSTF was undertaken without the involvement of NIA which was not in conformity with its mandate

  - In the implementation of the projects under the ISPSTF, NTA executed a tripartite MOA with identified LGUs and Farmer Cooperators (FCs) in the Provinces of Abra, Ilocos Norte, Ilocos Sur and La Union.  It was provided in the MOA that NTA will:

Constitute a Project Management Team (National Project Implementation Team) to be responsible for the overall planning, coordination, monitoring and evaluating the implementation of the project and recommend improvements, if necessary; and a Technical Team to conduct site inspection, periodic monitoring of construction works and to certify progress/status of completion, for purposes of fund releases. Xxx.

  - Since NIA has the mandate to plan, design, construct, and/or improve all types of irrigation projects, the overall supervision undertaken by NTA for 137 projects implemented by LGUs and the implementation of five projects by administration in the Municipalities of Sinait, Ilocos Sur and Solsona, Ilocos Norte were not in consonance with its mandate under EO No. 245 which states, viz.:

Xxx to: (a) improve the economic and living conditions and raise the quality of life of the tobacco farmers including those who depend upon the industry for their livelihood; and (b) promote the balanced and integrated growth and development of the industry and help make agriculture a solid base for massive industrialization.

  - This is a reiteration of the observation contained in previous AARs as NTA did not consider the involvement of NIA in the implementation of the ISPSTF despite it is not mandated to perform such functions under EO No. 245.  Further, the Audit Team believed that NTA has no technical expertise in the execution of irrigation projects.

Non-submission of certifications of NTA Accountant that funds amounting to P969.596 million previously transferred to the LGUs as implementing agencies have been liquidated and accounted for in         the books

  - Section 4(6) of Presidential Decree (PD) No. 1445 provides that “Claims against government funds shall be supported with complete documentation.”

  - Disbursements totaling P969.596 million as of year-end were not supported with the required Certifications by the Accountant that funds previously transferred to the IA had been liquidated and accounted for to support the validity of the transactions. The non-submission of the documentary requirement could be the subject of the issuance of Notice of Suspension in audit.

  - COA Circular No. 2016-002 dated May 31, 2016, re: Prescribing the Revised Guidelines and Documentary Requirements for Fund Transfers, provides that:

In line with the Commission’s commitment to safeguard public funds against misuse, and at the same time, to be an enabler of government programs and projects, the submission of the Certification by the Accountant that funds previously transferred to the Implementing Agency (IA) has been liquidated, post audited and accounted for in the books as part of the documentary requirements for fund transfers stated in Item 3.1.1 of COA Circular No. 2012-001 is hereby amended to read                 as follows –

Certification by the Accountant that funds previously transferred to the Implementing Agency (IA) has been liquidated and accounted for in the books.

Non-settlement/liquidation of funds transferred to 35 LGUs totaling                P113.090 million despite project completion

  - NTA transferred funds to the implementing LGUs by tranches. Verification of records showed that the remaining fund transfers for completed irrigation projects were unsettled/unliquidated as of year-end. Of the 146 irrigation projects for Batches I to III with approved budget cost of P1,115.800 million, remaining fund transfers for 35 completed projects in the amount of P113.090 million were unliquidated as shown in Annex B, while P96.723 million were still unreleased as of December 31, 2017.

  - The period for the completion of the projects was specified in the contracts. Although the projects were already 100 per cent completed, the accomplishment reports were not yet submitted. Inquiry revealed that the Municipal Mayor would only accept the completed irrigation project when an inspection thereof was undertaken by the COA Technical Audit Specialist (TAS) and, both the inspection and evaluation reports were submitted by COA and the Municipal Engineers.

Unutilized portion of funds totaling P398,354 were not refunded to NTA by 11 LGUs contrary to Item 4.9 of COA Circular           No. 94-013

  - Verification of the submitted supporting documents for the funds transferred to LGUs in CAR and Region I disclosed that funds were not fully utilized for the irrigation projects, leaving unexpended funds of P398,352 from Batches I to III. However, as at audit date, the unexpended/unused funds were not returned to NTA.

  - This was not in consonance with Item 6.7 of COA Circular No. 94-013 dated December 13, 1994, which provides that:

6.7.	The implementing agency shall return to the source agency any unused balance upon completion of the project.

  - Funds transferred to LGUs were intended for specific purposes, thus, any unutilized/unspent balances shall be returned to NTA and be reverted back at the end of the year to the Bureau of Treasury (BTr), the source agency.

A total of P3.669 million excess funds remained under the custody of NTA and were not reverted back to the BTr

  - The amount of P3.669 million was no longer released to several implementing LGUs because the projects were already 100 per cent complete.  This was based on the Inspection Reports submitted by the COA TAS and the Municipal Engineers.

  - Management informed that the unreleased portion of the funds was due to the 100 per cent completion of the project based on the Inspection Reports submitted by the COA TAS and Municipal Engineers. Thus, the remaining amount was no longer transferred to the implementing LGUs. The unreleased funds still remained in the custody of NTA and not reverted back to the BTr.

  - We reiterated our previous year’s audit recommendations that Management:

- Consider the involvement of NIA in the implementation of its on-going and succeeding irrigation projects under ISPSTFs since NIA has the mandate to plan, design, construct and/or improve all types of irrigation projects;

- Instruct the Accountant to prepare and submit the required certification on the funds transferred to LGUs in compliance with Section 4(6) of PD No. 1445 and COA Circular No. 2016-002 dated May 31, 2016;

- Send Demand Letters to LGUs with unliquidated fund balances for completed irrigation projects and, set/provide time frame to implement the projects as planned so that intended beneficiaries could timely benefit therefrom; and

- Require the concerned LGUs to return the unutilized/unexpended portion of funds to NTA in compliance with COA Circular No. 94-013.

  - We, likewise, recommended that Management revert back to the BTr the unreleased balances, in compliance with Item 4.9 of COA Circular No. 94-013 dated December 13, 1994.

  - Management commented that they were in coordination with NIA Officials for the Batch IV irrigation projects. A MOA was already signed by NTA and NIA. Management also committed to address first the deficiencies in Batches I, II and III before proceeding with the Batch IV of the projects.

  - As to the unutilized/unexpended portion of the funds, Management informed that they will request from DBM the authority to use the funds for the existing irrigation projects that need additional funds, as long as the concerned LGUs will execute waiver that they are no longer interested and, it will be approved by the Members of the Governing Board.

Integrated Farming and Other Income Generating Activities Project – Tobacco Contract Growing System (IFOIGAP – TCGS)

- Procurements of farm inputs specifically fertilizers and pesticides by NTA – Central Office (NTA – CO) for delivery to NTA La Union, Candon, Pangasinan, Cagayan and Batac Branches and distribution to farmer-beneficiaries in the form of loans under the IFOIGAP – TCGS, were not in accordance with the Farm Plans and Budget (FPB) of NTA and principles of a sound public procurement system, thus, defeating the purpose of competitive public bidding.

  - For CY 2017, NTA had complied with the provision of Section 10 of RA No. 9184 on competitive public bidding.  However, examination of the various procurement processes of farm inputs specifically fertilizers and pesticides by NTA – CO for delivery to NTA La Union, Candon, Pangasinan, Cagayan and Batac Branches and distribution to farmer-beneficiaries in the form of loans under the IFOIGAP – TCGS, showed that the Agency did not strictly follow the governing principles of a sound government procurement system.

  - Item 3, Section 55 of PD No. 1445 provides that, “[A]n evaluation shall be made of the system of internal control and related administrative practices to determine the extent they can be relied upon to ensure compliance with laws and regulations and to provide for efficient, economical and effective operations.” (Underscoring supplied)

  - The procurement of farm inputs was centralized in NTA CO so as to primarily avail of bulk discount, encourage transparency in the procurement process and ensure compliance with the requirements of RA No. 9184, otherwise known as Government Procurement Reform Act.

In-depth planning was not conducted in the procurement of the farm inputs

  - In determining the farm input requirements, Branch Offices relied on the report of the Technician who conducted actual inspection and discussion with the tobacco farmers as to the procurement of needed farm inputs. This report was collated by the Branches and submitted to the NTA CO for the latter to purchase and deliver the items.

  - However, the NTA CO purchased the items based on the service area as reported which might not be updated, likewise the pesticide for tobacco in the area may not be appropriate.

  - The Consolidated FPB was not adhered strictly in purchasing the farm inputs. The FPB shows the amount of needed assistance, including the quantity needed for farm inputs by farmers based on the tobacco farm area with their designated assisting Extension Worker (EW).

  - The consolidated FPB should be the basis of the CO in placing orders of farm inputs for delivery to the Branches. However, deficiencies were noted in the deliveries as discussed below:

- In La Union Branch, 1,642 items of farm inputs amounting to P1.883 million were considered over supply or above the required farm inputs needed by the 981 farmer-availees of the loan assistance, in excess of the total budget of P12.868 million for the farm inputs. Interview with the Officer-in-Charge of the project revealed that the excess supply would be distributed to interested farmer-cooperators who were willing to avail additional loan from the Branch. However, inventory of the items on hand showed that there were 1,418 farm inputs as of December 31, 2017.

- In NTA Candon Branch, there were excessive deliveries of 8,153 items of pesticides with a total value of P1.444 million. There was no available storage room for the safekeeping of these items, and these would become trash if not utilized or properly kept.

- In Pangasinan Branch, the farm inputs amounting to P2.769 million remained undistributed as of December 31, 2017. Likewise, there were           1,520 items which were under delivered and 5,173 that were over delivered.

- In Batac Branch, over deliveries of pesticides amounted to P0.632 million.

  - The above observations had been communicated to NTA top Management since the public bidding was done at the CO.  The top Management explained that excess deliveries were mainly due to the difference in the consolidated estimate of farm requirements based on land area and consolidated actual farm requirements when these farm inputs were actually delivered to the Branches.  An estimate based on land area is needed since the bidding process takes about one to two months.  If no estimate is made or if NTA CO would wait for the actual farm requirements, the bidding process would be delayed and the farm inputs would not reach the farmers on time.

Late deliveries of farm inputs and difficulty of unloading farm inputs from designated drop-off points to the farmer-beneficiaries

  - In Cagayan Branch, a total of 1,117 bags of fertilizers amounting to P0.883 million were received on July 19 and 20, 2017 from Universal Harvester, Inc. and distributed to farmers on July 28 to September 27, 2017, or two months after the beginning of plantation, hence the fertilizers were used for corn and vegetables since the transplanting of rice had been completed.

  - Due to the delay in the delivery of fertilizers, less number of farmers availed of the program in CY 2018.  One of the availees mentioned that if the fertilizers would be delivered late again, he has no other recourse but to personally buy the needed fertilizers for the coming cropping season, which would mean a cancellation of the loan.

  - Moreover, it was observed that deliveries were done at different drop-off points, where the farm inputs could not be properly secured. Sometimes, deliveries were made simultaneously at the different drop-off points where the Property Officer could not witness all at the same time. In addition, some drop-off points do not have any form of protection for the inventories; thus, exposing farm inputs to harmful elements when not immediately delivered to end-users.

  - Additional costs were incurred for handling and transport of the farm inputs. Whenever the Branch had to move the inputs to another location, the EWs had to spend for labor cost. In addition, the farmers themselves had to pay for transportation costs from the drop-off points to their place of residence. The burden of freight costs, however, was often shifted to the assigned EWs who in turn assume the cost just to facilitate           the delivery.

  - It was also noted that some farm inputs could be availed of at a lower price when purchased in the province or other provinces near the vicinity of the NTA Branches, not to mention the added cost for transporting the farm inputs from Manila to the               Regional Branches.

The Bids and Awards Committee (BAC) of the Branches was not utilized for the procurement of farm inputs.

  - Since public bidding was done at the CO, the BAC of the Branches was not utilized.  Section 11 of Republic Act (RA) No. 9184 requires each procuring entity or government agency to establish a single BAC of its procurement.

  - The BAC in the Branch level convenes only during the conduct of small value procurement; hence, the purpose for its creation as required by the procurement law was served. However, public bidding can be decentralized as a function of the BAC in the Branches, subject to limitation.

  - The CO needs to consolidate all the farm requirements of all Branches, requiring longer lead time in order to have a timely public bidding. It might be better if the BAC of the Branch tackles the procurement of farm inputs.  If the procurement of farm inputs be transferred to the Branch level, a more accurate data or estimate could be gathered, since the lead time would be cut short due to elimination of the consolidation of farm input requirements of the Branches by the CO.

  - In view of the foregoing, it can be assumed that if public bidding be conducted at the Branch Offices, it might be more advantageous to the Agency and the farmer-beneficiaries and, the governing principles of a sound public procurement system may be achieved.

  - We recommended that top Management:

- Look into the problems encountered by the Branch Offices in the delivery and distribution of farm inputs to farmer-availees;

- Ensure that deliveries to the Branches are based on the consolidated FPB with reasonable estimates of farm inputs to avoid significant over and/ or under deliveries; and

- Consider transferring the procurement activities of farm inputs to the Branch Offices to minimize incidental costs such as handling, transportation and storage.

  - Management commented that the fertilizers/pesticides were purchased through competitive bidding. The Board approved the request of the Pangasinan Branch Office to use the fertilizers and pesticides which were undistributed during the tobacco season for rice production in CY 2018. As of March 31, 2018, the balance was P2.154 million. Said amount was further decreased to P0.928 million, since P1.226 million was used for the rice project. Also, in Cagayan Branch, the fertilizers/pesticides were already fully distributed to employees who are also farmers to be paid on installment basis.

  - As a rejoinder, the Audit Team took note of the comments of Management and would monitor Agency’s implementation of the above-mentioned recommendations in CY 2018.

GENDER AND DEVELOPMENT (GAD)

- The CY 2017 GAD Plan and Budget (GPB) was not submitted to Philippine Commission on Women (PCW) for review and approval, contrary to                   PCW Memorandum Circular No. 2014-04 dated September 29, 2014; thus, the responsiveness to gender issues of the activities undertaken could not be evaluated.  Likewise, the Agency was unable to create a GAD Focal Point System in Abra, Vigan and La Union Branches which is not in accordance with                 RA No. 7192, otherwise known as “Women in Development and Nation Building Act” and Sections 2 and 3.5 of PCW-National Economic and Development Authority (NEDA)-DBM Joint Circular No. 2012-01. Moreover, in Cagayan Branch, GAD Database was not created contrary to Section 37.D, Rule VI of the Implementing Rules and Regulations (IRR) of RA No. 9710, thereby reflecting lack of gender sensitivity in the operations of the said Branch.

  - Section 2.3 of PCW-NEDA-DBM Joint Circular No. 2012-01 dated August 22, 2012 provides that:

Pursuant to the [Magna Carta for Women] MCW and the General Appropriations Act (GAA), all government departments, xxx, government-owned and controlled corporations (GOCCs), xxx shall formulate their Annual GPBs within the context of their mandates to mainstream gender perspectives in their policies, programs and projects. GAD Planning shall be integrated in the regular activities of the agencies, the cost of implementation of which shall be at least five percent (5%) of their total budgets. Xxx.

  - Section 37 A(1)(f) of the IRR of RA No. 9710 or the Magna Carta for Women on the Planning, Budgeting and Evaluation for GAD in the development of and budgeting for GAD Plans and Programs, states that:

(f) The PCW shall review the GAD Plans, Programs, and Budgets accompanied by GAD Accomplishment Reports submitted annually by the NGAs, bureaus, SUCs, GOCCs, and other government instrumentalities for gender-responsiveness. The PCW shall then return the endorsed GAD Plans and Programs to the concerned agencies for submission to the DBM. The agencies shall submit to the DBM their PCW-endorsed GAD Plans, Programs, and Budgets along with the annual agency budget proposals.

  - The DBM-approved Corporate Operating Budget (COB) of NTA included an allocation of P42.280 million for the implementation of GAD Programs, Activity and Projects (PAPs) for CY 2017. However, only P30.104 million or 71.20 per cent was expended out of the allocated budget.

  - Comparison of GAD targets based on DBM-Approved Budget against actual accomplishments under GAD Accomplishment Report (AR) disclosed that some targets were met, while several were not; and some activities exceeded the targets, as presented in Table 7.

Table 7 - Comparison of GAD Targets against Actual Accomplishments

| GAD Program/Activity/Project | Accomplishments Per Performance Indicators |  | Cost (in Thousand) |  |
| --- | --- | --- | --- | --- |
|  |  |  | DBM GAD Approved Budget | Actual Accomplishment |
|  | Target | Actual | (a) | (b) |
| Integrated Farming and Other Income Generating Activities Project (IFOIGAP) - Tobacco Contract Growing System - Rice Production Project | 900 550 | 712 556 | P 13,500 4,950 | P 13,904 5,443 |
| Seed Production and Distribution | 900 | 700 | 200 | 156 |
| Communication Support Program | 5,000 | 5,000 | 150 | 220 |
| AGRIPINOY Tobacco Farmers Trading and Food Processing Center (TFTFPC) | 150 | 31 | 12,300 | 2,542 |
| Renewable Fuelwood Energy Farm Development Project and Restoration of Ecological Integrity (RFEFDPREI) | 300 | 350 | 9,000 | 6,818 |
| Farmers Organizational Development (FOD) - Capability Building/Leadership Development | 100 | 237 | 300 | 163 |
| Scholarship Program for Children of Tobacco Farmers in compliance to RA No. 9211 | 230 | 84 | 1,610 | 588 |
| Institutional Development/ Extension Support for Education and Training Services (ESETS) | 24 | 24 | 70 | 70 |
| Institutional Development - GAD related trainings/activities | 200 | 200 | 200 | 200 |
|  | 8,354 | 7,894 | P 42,280 | P 30,104 |

  - Further, the same observations as in previous AARs were noted in CY 2017 audit of GAD, such as:

- The NTA GPB for CY 2017 submitted to the DA was not submitted to PCW for review, approval, and endorsement to the DBM for budget proposals;

PCW Memorandum Circular No. 2014-04 dated September 29, 2014 was issued for the preparation and online submission of Fiscal Year (FY) 2016 GPBs and   FY 2014 GAD ARs and other matters. Paragraph 2, Item A of the said Memorandum Circular specifically states that:

To facilitate the GAD planning and budgeting process, the PCW shall be implementing the online submission, review and endorsement of GPBs and GAD ARs through the Gender Mainstreaming Monitoring System (GMMS), an online system for managing GAD profiles, GPBs and GAD ARs, as well as for generating GAD-related reports.

Despite previous years’ audit observations and recommendations, NTA’s GPB for CY 2017 was not submitted to PCW for review, approval, and endorsement to DBM for budget proposal purposes. It was also noted that NTA only enrolled in PCW Gender Mainstreaming and Monitoring System (GMMS) in January 2018, thus, the Agency was not able to submit its CY 2017 GPB and GAD ARs online. Nevertheless, the person in charge of GAD informed that for CY 2018, they would comply with the online submission as required by PCW.

- The targeted number of beneficiaries for four  GAD activities were not met, such as the provision of:

- tobacco production/technical/marketing assistance under IFOIGAP;

- seeds to farmer cooperators;

- hog production/technical/marketing assistance under AgriPinoy; and

- financial assistance to tobacco farmers’ children enrolled in state colleges and universities in Regions I, II and CAR.

- It is noteworthy to mention that based on the output performance indicators, six projects were accomplished and, even exceeded the targets composed of:   (i) IFOIGAP project (Rice Production Project); (ii) Communication Support Program; (iii) Renewable Fuelwood Energy Farm Development Project and Restoration of Ecological Integrity; (iv) Farmers’ Organizational Development; (v) Institutional Development/ESETS and (vi) GAD related trainings/seminars/ activities for women employees.

- Likewise, it is worth mentioning that from the GAD AR, the actual accomplishment under the Renewable Fuelwood Energy Farm Development Project and Restoration of Ecological Integrity of 350 beneficiaries exceeded the target of 300 and, the actual cost incurred of P6.818 million was lower than the budget of P9 million. The actual accomplishment under FOD-Capability Building/Leadership Development of 237 beneficiaries exceeded the target of 100 and, the actual cost incurred of P163,000 was lower than the budget             of P300,000.

  - However, the Agency was not able to create a GAD Focal Point System in Abra, Vigan and La Union Branches contrary to RA No. 7192, otherwise known as “Women in Development and Nation Building Act” and Sections 2 and 3.5 of PCW-NEDA-DBM Joint Circular No. 2012-01.

  - Government agencies were mandated to institutionalize GAD in government and to incorporate and reflect GAD concerns in their agency performance commitment, annual budget proposals, and work and financial plans pursuant to RA No. 7192.

  - Likewise, Section 3.5 of PCW-NEDA-DBM Joint Circular No. 2012-01          states that:

Agency GAD Focal Point Systems (GFPS) shall take the lead in mainstreaming gender in agency PAPs. As such they shall coordinate the preparation of the agency GPB and the GAD AR, monitor its implementation and report on its results. In the process, they shall provide technical assistance to offices or units within their agency on gender mainstreaming. To enable them to perform their roles, it is important that GFPS members are provided with the required gender capacity, such as the application of gender analysis tools.

  - Management confirmed that no GAD Focal Point System was created in the Branches in 2017. Hence, no one has taken the lead in mainstreaming gender throughout NTA’s Branches and offices. As a result, gender issues and concerns in the Branches may not be properly addressed.

  - Moreover, in Cagayan Branch, the GAD Database was not created contrary to Section 37.D, Rule VI of the IRR of RA No. 9710, thus, reflecting lack of gender sensitivity in the operations of the said Branch.

  - Section 37, Rule VI of the IRR of RA No. 9710 provides:

Gender Mainstreaming as a Strategy for Implementing the Magna Carta of Women – xxx

D. GAD Database – All departments, including their attached agencies, offices, bureaus, SUCs, GOCCs, LGUs, and other government instrumentalities shall develop and maintain a GAD database containing GAD information to include gender statistics and age- and sex-disaggregated data that have been systematically produced/gathered, regularly updated to serve as inputs or bases for planning, programming, and policy formulation. Xxxx

  - Evaluation of NTA Cagayan Branch submitted GPB with attachments disclosed some lacking GAD mainstreaming essentials like sex and age-disaggregated data and gender statistics. Without the GAD database, gender-based issues that should be addressed through GAD PAPs could not be readily identified by the Branch.  Further, no Violence Against Women and Children (VAW) Help Desk was created in the workplace to prevent or address violence against women and children.

  - We recommended and Management agreed to:

- Henceforth, submit the NTA Annual GPB to PCW for review, approval and endorsement to the DBM, to ensure that the GAD related activities undertaken during the year are responsive to the identified gender issues and that these gender issues are fully addressed;

- Maximize, with consideration to economy, the fund allocated for GAD and implement the programs and projects effectively in accordance with the PCW-endorsed GPB;

- Create a GAD Focal Point System in the Branches that shall take the lead in mainstreaming GAD in their PAPs; and

- Create and institutionalize the GAD Database pursuant to Section 37.D, Rule VI, of RA No. 9710, to serve as inputs in GAD planning, monitoring, and evaluation.

  - Management informed that women were always involved in various projects of NTA. Also, NTA–CO enrolled in the PCW GMMS this January 2018; thus, the GPB for     CY 2019 and GAD AR for CY 2018 were already submitted through GMMS of PCW, which the latter had given their comments on how NTA can improve their GAD activities.

  - In Cagayan Branch, Management explained that no GAD Focal Point System had been established for the Branch GAD-related activities and it acceded with the recommendation.

COMPLIANCE WITH TAX LAWS

- NTA regularly complies with the requirement of the Department of Finance (DOF) - DBM - Commission on Audit (COA) Joint Circular No. 1-2000 dated January 3, 2000 and Joint Circular No. 1-2000A dated July 31, 2000, relative to the withholding of taxes on gross compensation income of personnel, suppliers and clients for procurements and service contracts which were remitted using the prescribed Bureau of Internal Revenue (BIR) forms. The year-end balance of Due to BIR in the amount of P3.559 million was remitted in January 2018.

COMPLIANCE  WITH GOVERNMENT SERVICE INSURANCE SYSTEM (GSIS) ACT

- The provisions of Section 6 of RA No. 8291 on the withholding of contributions and remittance of employees’ and employer’s share to the GSIS within the period prescribed under the said Act were duly complied with.

- PERFORMANCE

Renewable Fuelwood Energy Farm Project and Restoration of Ecological Integrity (RFEFPREI)

- The Farmer-Cooperators (FCs) under the Kahuyang Pangkabuhayan at Pangkalikasan (KPP) component of the RFEFPREI were not able to harvest fuelwood  in 2017 due to: (a) some planted trees did not survive natural calamities in 2015 and 2016; (b) some trees were not ready for harvest since the desirable size for fuelwood was not attained; and (c) full grown trees were not cut due to the regulations of the Department of Environment and Natural Resources (DENR) and Local Government Units (LGUs); thus, resulting in low collection of production assistance granted to the FCs in 2013 and non-attainment of the specific objectives of the project which were to supply and augment the energy-fuelwood requirement of the flue-curing Virginia tobacco leaf and promote the creation and development of livelihood enterprises for the tobacco growing communities. Moreover, in view of the inability of NTA to fully attain the objectives of the KPP, the project might not be able to contribute to the achievement of the Sustainable Development Goals (SDGs) of No Poverty (Goal 1) and Life on Land (Goal 15) related to the project’s objectives.

  - NTA conceptualized the RFEFPREI in 2013. The project was designed as a comprehensive, self-generating industry intervention, generally aimed to improve the living conditions and betterment of quality of life of the population in the tobacco growing regions. More specifically, the project aimed to:

- Restore the ecological integrity of the tobacco growing regions and contribute in the government’s mitigation effort against flash flooding, soil erosion and other calamities;

- Supply and augment the energy-fuelwood requirement of the flue-curing Virginia tobacco leaf;

- Provide watershed factor to replenish fresh water used by household and for irrigation; and

- Promote the creation and development of livelihood enterprises for the tobacco growing communities.

  - The project has two components, namely: (a) Tree Seedling Nursery Production and Distribution and (b) Fuelwood Farm under the KPP. It also includes Synchronized Tree Planting activity in the eight Branch offices of NTA in collaboration with the DENR, to be participated by the different government agencies, LGUs, tobacco companies, tobacco farmers and families, students (secondary schools), and civil society organizations. The project commenced in the year 2013 and, the grant of loans to borrowers-availees also started in the same year.

  - The following were observed in the implementation of the project:

The FCs were not able to harvest and market fuelwood in CY 2017, resulting in low collection of the financial assistance/loans granted by NTA

  - One of the implementing strategies of the project was to extend production assistance/loans to qualified tobacco farmers under the KPP component. The FCs would then use the production assistance to cover the expenses from seedling production to growing of trees. The production assistance was granted to the FCs in the form of a loan; hence, to be collected. Given the rotation period of four years, the loans maturing in 2017 were those production assistance released in 2013. The report from the Finance Department showed that the collections in 2017 for the KPP production assistance amounted to P147,295 or 0.45 per cent of the total fund released to FCs in 2013 of P33.024 million, as shown in Table 8.

Table 8 – Status Report on the Collection of Production Assistance in CY 2013

|  | Fund Release | Collections (as of 09/30/2017) | Balance | Collection Efficiency |
| --- | --- | --- | --- | --- |
| Tree Production | 30,098,970 | 143,961 | 29,955,009 | 0.48 |
| Bamboo Production | 2,925,202 | 3,334 | 2,921,868 | 0.11 |
|  | 33,024,172 | 147,295 | 32,876,877 | 0.45 |

  - The Chief Accountant and the OIC-Manager of the Corporate Planning Department (CPD) explained that the FCs made payment out of their own money, since there was no harvest from the trees planted in 2013, due to the following:

- Some planted seedlings did not survive the El Niño in CY 2015 and the typhoon Lawin in CY 2016;

- Planted trees were not ready for harvest, since the desirable size for fuelwood was not attained as a result of the project cycle that does not match the planting calendar due to fortuitous events and change in weather conditions that were beyond the control of NTA; and

- Full grown trees that were ready for harvest were not cut due to the regulations of the DENR and the LGUs that prohibit the cutting of trees unless some documents are presented, such as land titles, which the farmers could not easily provide.

  - In addition, the Audit Team gathered from the Manager of the Finance Department and the OIC-Manager of the CPD that the Consultant, who is a licensed forester, conducted a rapid assessment of the KPP project specifically its performance vis-à-vis its objectives and was able to identify the following deficiencies:

- Lack of systematic monitoring process of the project to ensure that planted seedlings would be taken care of until they would become full grown trees; and

- Lack of experts and external assistance on the project evaluation and approval system to ensure that deficiencies of the project proposals were corrected.

  - The implementing guidelines provide that under the KPP, a 20 per cent mortality rate is permissible or a survival rate of 80 per cent as success indicator. However, the status and monitoring report of Management showed that the success indicator             was not met.

  - Despite the full financial assistance granted to the FCs to cover expenses from seedling production to grown-out trees, the 80 per cent survival rate was not achieved.

  - The Audit Team also noted that there were no standard specifications set by the NTA in determining the survival rate of the planted seedlings; thus, there was no basis of measurement of the accomplishments of the FCs to determine their compliance on the 80 per cent survival rate. Hence, the reported survival rates of the seedlings might not be reliable. The important data such as the height and diameter of the seedlings planted in comparison with the grown-out trees standard growth were not indicated in the report to gauge the growth of the trees and determine the efficiency in utilization of the budget/financial assistance in the maintenance and sustenance of the seedlings.

  - Further, under the Synchronized Tree Planting (STP) scheme, there were also no implementing guidelines in monitoring the maintenance and sustenance of planted seedlings given for free to different schools, organizations, barangay residence, etc. No MOA or Agreement Form was prepared before issuing free seedlings for Tree Planting Activity to assure the care and protection of planted seedlings.

  - Also, verification of the attendance sheets of the participants in the Tree Planting Activity disclosed that the elementary students were the ones mostly involved in the said event. It was worth mentioning that students young at age as eight to ten years old were engaged in this community service and would serve as a platform for pupils to get closer to nature. However, it was distressing to note that these pupils were required to plant 10 to 35 seedlings for this one-day occasion. Planting trees for a greener environment takes a degree of skill and knowledge to make it successful. That was another reason why the success indicator for the tree planting project might not be achieved.

  - Lack of proper monitoring in the maintenance, sustenance and protection of planted seedlings or the so-called “post-planting care” might increase the likelihood of a high mortality rate in seedlings planted and might result in wastage or loss of government funds.

  - It was also observed that the eligibility requirement for the FCs contained in the Implementing Guidelines and Procedures of the project does not include a provision that the FC should own the parcel of land to be used as planting sites. This was the reason why the FCs could not easily provide the land titles for the application of tree cutting permit since majority of the FCs who availed of the production assistance were only tenants of the land that they made available for the project. It was also noted that the project evaluation team of the NTA did not coordinate with the DENR during the planning phase of the project to ensure that the project implementation would be in accordance with DENR’s policies and regulations that would impact on harvesting of fuelwood.

  - In effect, since there was no harvest of fuelwood which the FCs could have marketed/sold to earn additional income, there was minimal/non-payment of the production assistance granted to FCs in the form of a loan.  Section VII B.7. of the MOA between the NTA and the FCs requires the former to “Repay production assistance conscientiously in accordance to pre-approved terms and payment schedule.” Furthermore, penalty charges will be added to the FCs’ loan obligation in accordance with Section VI of the MOA which states that, “Delayed repayments and/or remittances of collections shall be subject to a penalty charge of three percent (3%) for every month.”

  - Considering that the NTA was not able to fully attain the specific objectives of the KPP, the project might not be able to contribute to the achievement of the SDGs related to its objectives.

  - The SDGs are also known as the Global Goals. The SDGs are new, universal set of goals, targets and indicators that United Nations (UN) member states would be expected to use to frame country agenda and policies over the next 15 years. It consists of 17 goals, 169 targets and 232 unique indicators. For the countries to achieve the SDGs, they must get not only additional financial resources from both domestic and external sources but should also formulate policies and set up an institutional environment that would ensure that the resources were used efficiently and effectively.

  - As part of the commitment of the Philippines to monitor the SDGs, the Philippine Statistics Authority (PSA) Board, through PSA Resolution No. 04, Series of 2016, re: Enjoining Government Agencies to Provide Data Support to the Sustainable Development Goals (SDGs), enjoined all government instrumentalities to provide the necessary data support to monitor the country’s performance vis-à-vis the SDGs based on the indicator framework that shall be determined by the National Economic and Development Authority (NEDA), PSA and other government agencies.

  - Anent thereto, the NTA identified the SDGs to be addressed by their existing programs/projects and identified Goal 1 – No Poverty and Goal 15 – Life on Land relevant to the specific objectives of the RFEFPREI.

Goal 1 – No Poverty

  - The Corporate Planning Department (CPD) identified Goal 1 as the SDG related to the specific objective of the KPP component of the RFEFPREI, since it envisions to provide additional income for the farmers that will contribute to reducing poverty.  Goal 1 – No Poverty targets to end poverty in all its forms everywhere.

  - The zero/minimal payment on loan collection as discussed in the preceding paragraph was one of the consequences of the problems in the implementation of the KPP which resulted in FCs’ inability to earn additional income and adversely affected their capacity to pay the loans to NTA, including the interest and penalty charges.

  - Hence, NTA was not able to attain the objective of the KPP to provide additional income to the farmers. There was also additional burden to the farmers in the form of interest and penalty charges that might hinder project’s contribution to the achievement of SDG Goal 1 – No Poverty.

Goal 15 – Life on Land

  - The RFEFPREI was conceived by the NTA primarily because the continuing development of the tobacco industry had been confronted with the issue on the use of forest resources for curing fuel and other purposes. It was also the basis in formulating project’s main objectives such as to: (a) restore the ecological integrity of the tobacco growing regions and contribute in the government’s mitigation effort against flash flooding, soil erosion and other calamities; and (b) supply and augment the energy-fuelwood requirement of the flue-curing Virginia tobacco leaf.

  - In relation thereto, the NTA identified Goal 15 as the SDG related to the main objectives of the project. Goal 15 – Life on Land aims to protect, restore and promote sustainable use of terrestrial ecosystems, sustainably manage forests, combat desertification, and halt and reverse land degradation and halt biodiversity loss.

  - The assessment report submitted by the Consultant disclosed that some 32,295 m3 of fuelwood could be harvested from the 2013 plantings. The estimated harvest was about 10 per cent of the expected yield of the 1,187 hectares (Ha) planted in the same year and could cover five per cent of the fuelwood requirements for 50,000,000 kg of Flue-Cured Virginia (FCV) of 300,000,000 kg computed at 6 kg per kg of FCV.  The 300,000,000 kg fuel requirement is equivalent to 600,000 m3;; hence, the estimated fuel harvest of 32,295 m3 can cover five per cent of this requirement. Details are presented  in Table 9.

Table 9 – Estimated Fuelwood Harvest from the 2013 Plantings

| - Area planted | - | 1,187 Ha |
| --- | --- | --- |
| - Estimated Fuelwood harvest | - | 32,295 m3 |
| - FCV production target | - | 50,000,000 kg |
| - Fuelwood requirement (kg) (6 kg/kg of FCV) | - | 300,000,000 kg |
| - Fuelwood requirement (m3) (500 kg/m3) | - | 600,000 m3 |
| - % of harvestable Fuelwood | - | 5% |

  - Analysis of the above data revealed that the estimated fuelwood harvest of 32,295 m3 from the 2013 plantings could not supply the fuelwood requirement for the FCV production for 2017. From the given information, it can be derived that out of the 600,000 m3, the remaining 567,705 m3 or 283,852,500 kg of fuelwood requirement for the FCV production would still be harvested from the forest resources and approximately 20,000 hectares of trees would be cut to satisfy the fuelwood requirement.

  - Thus, NTA needs to accelerate the implementation of KPP project by expanding the areas to be planted and increase the harvest to supply and augment the energy-fuelwood requirement of the flue-curing Virginia tobacco leaf that would contribute to the attainment of the SDG Goal 15 – Life on Land.

  - We recommended that Management:

- Instruct the Project Management Team (PMT) and the Provincial Branch Project Management Team (PBPMT) to look into the problems encountered in the implementation of the project and determine the appropriate actions to address the deficiencies hindering the attainment of the targeted production, to be able to supply the fuelwood requirement in flu-curing of tobacco leaf;

- Strengthen the project monitoring process from seedling production to growing of trees to ensure the proper maintenance and sustenance of seedlings planted as well as the evaluation process to address the deficiencies in the implementation of the project;

- Coordinate with the DENR and LGUs for the harmonization of their policies and regulations that have impact on harvesting and marketing of fuelwood aspect of the project, in order for the FCs to proceed in harvesting and to cash-in their fuelwood produce so that they will be able to settle their loan obligations to NTA; and

- See to it that careful planning is undertaken in the conceptualization of projects to be implemented to ensure attainment of the desired objectives and at the same time to contribute in the achievement                 of the SDG.

  - Management informed that a Consultant was hired to evaluate the KPP project and the recommendations. The Branch Offices Managers have already coordinated with DENR and still awaiting their action on the request to cut the harvestable fuelwood.

  - Additionally, the NTA Governing Board decided that the guidelines for implementation of the project should be reviewed and the grant of loans to the farmers will be temporarily suspended.

  - As a rejoinder, the Audit Team acknowledged Management’s initial action to address the problems encountered in the implementation of the project.  The extent of their implementation of the above-mentioned recommendations will be monitored           in CY 2018.

Tobacco Dust Production Agribusiness Project (TDPAP)

- The TDPAP located in Sto. Tomas, La Union incurred a total loss of   P32.883 million since it started operations in 2009 due to poor planning and execution thus, casting doubt on the ability of NTA to pursue the objective of the project. In addition, the Employees’ Quarter of TDPAP with a net book value of P0.879 million remained idle.

  - The TDPAP is a project conceptualized by NTA to introduce other uses of tobacco plant and alternative product that can be provided to tobacco farmers, whose crops were threatened and endangered due to world-wide massive campaign against smoking that might bring adverse effects to the livelihood of the tobacco farmers. Furthermore, the development and commercialization of the other industrial uses of tobacco, particularly the tobacco dust, was used as organic pesticides to replace and ban the highly toxic, cyanide-based chemicals used in aquaculture. This created more jobs and raised the quality of life of the tobacco farmers.

  - The NTA projected that it would earn an income amounting to P265.889 million in five years. However, contrary to what had been projected, audit of the financial performance of the project revealed that it had been incurring losses since it started operation in mid-2009, which already accumulated to P32.833 million in 2017, as summarized in Table 10.

Table 10 – Summary of Losses of TDPAP

| Year | Net Loss |
| --- | --- |
| 2009-2010 | P 3,576,387 |
| 2011 | 2,084,300 |
| 2012 | 1,821,124 |
| 2013 | 1,956,229 |
| 2014 | 1,792,328 |
| 2015 | 5,496,458 |
| 2016 (corrected) | 11,011,231 |
| 2017 | 5,094,696 |
|  | P 32,832,753 |

  - The continuing loss was attributed to the following:

- Since it started operation, the plant had earned income amounting to P4.922 million only while its expenses reached P37.754 million as at December 31, 2017. This simply showed that the expenditures of the project could not be sustained by its sales; thus, additional inflow from the funds of the NTA to TDPAP was needed to continue its operations.

- The high production and operating costs which reached P34.861 million divided by the actual production of 43,034 bags as of December 31, 2017 disclosed an average cost of P810.09 per bag, which could hardly break even with the prevailing sale price of P150.00 per bag. As a result, a loss of      P660.09 would be incurred for every bag of tobacco dust produced.

  - There was low production because of the low demand. TDPAP lost its biggest customer when a fire occurred in August 2016. Even with the low production, the operating cost remained high due to the high fixed cost, such as electricity and personnel services. Management informed that to further increase sales, NTA never stopped campaigning to prospective customers around Region 1 and nearby areas to market their product through distribution of flyers and conduct of product information dissemination, seminars and dialogue with fisher folks to introduce the product.

  - Further verification revealed that CY 2017 sales went down by P0.733 million or 51.66 per cent compared to last year’s sales of P1.419 million.

  - According to the Project Manager, this was due to the fire that happened at the plant site which caused the project to temporarily cease production that affected the sales, since they can no longer serve their customers. The P8.00 million insurance proceeds received remained unutilized and was deposited at the Branch’s bank account.

  - Despite the all-out support of various government agencies such as the Fertilizer and Pesticides Authority (FPA), Department of Agriculture (DA), Bureau of Fisheries and Aquatic Resources (BFAR), Department of Science and Technology (DOST), and the Bureau of Food and Drug (BFAD), to the product, which was certified as pesticide and fertilizer in one for it safety, effectiveness and standardized quality, sales were weak as evidenced by the sales record.

  - Inquiry with Management revealed that if the demand and production would increase, the sales would increase and it might be possible to cover the expenditures with the sales. Management had committed that there would be an increase in sales in CY 2018. They were also coordinating with various suppliers and customers for the improvement of financial performance and the operations of the project.

  - Indeed, the TDPAP was a great project to venture into because of its enumerated benefits; however, a project of this magnitude needs a thorough study and assessment. Otherwise, it would only cost funds to the government that would not sustain the implementation of the project.

  - In addition, the Employees’ Quarter of TDPAP in La Union Branch with a net book value of P0.879 million remained idle for eight years which leads to its further deterioration and substantial damage thereby depleting its economic value without any gain derived therefrom, thus resulting in wastage or loss of government funds.

  - We reiterated our recommendations that Management:

  - Enhance marketing strategy specially in the information dissemination aspect to promote the use of tobacco dust as an organic fertilizer and to increase the sales/revenue of the project, considering that the by-product is organic which is effective for fishponds and the environment as a whole;

  - Develop alternative business option for the tobacco dust plant in the event that it will no longer pursue its operation such as offer for lease or disposal of the plant so as not to waste government funds and              property; and

  - Study prudently the status and possible utilization of the Employees’ Quarter of TDPAP and develop an alternative use for it so that economic value will be derived. Moreover, assess the benefits that can be derived therefrom over the cost to prevent further wastage of funds.

  - Management pointed out that due to the fire that happened last August 2016, the production was temporarily stopped that affected their sales. Nevertheless, production using the tobacco dust machine that was used in Bulacan was resumed only on May 8, 2017. The repair of the plant is programmed for CY 2018. In addition, NTA renewed its marketing tie up with its biggest distributor to assure sale. Meanwhile, the Employees’ Quarter is currently utilized as stockroom since it was no longer safe to be used as Employees’ Quarter, but a study will be undertaken to make it income generating.

  - Management also commented that for the ensuing years, the plant would generate positive results due to the decrease of the cost of the raw materials from   P8.31 per kilo to only P0.80 per kilo.

Agripinoy Tobacco Farmers’ Processing and Trading Center (NTA AgriPinoy)

- AgriPinoy Milling Complex worth P83.075 million was not utilized for its intended purpose resulting in wastage of government funds.

  - AgriPinoy Milling Complex was constructed to cater the feed requirements of the hog production project of the AgriPinoy Tobacco Farmers Food Processing and Trading Center, where the NTA spent a total amount of P83.075 million. Its purpose was not attained due to the non-utilization of the project since its construction in 2013.

  - Aside from the cost of investment, expenses are likewise incurred for the maintenance of its facilities. Table 11 shows total expenses of P0.979 million incurred during the years 2015 to 2017.

Table 11 – Expenses incurred in AgriPinoy Milling Complex

|  | 2015 | 2016 | 2017 | Total |
| --- | --- | --- | --- | --- |
| Electricity | P 76,472 | P 289,281 | P 132,704 | P 498,457 |
| Security Services | - | 147,913 | 295,826 | 443,739 |
| General Services | - | 30,617 | 5,721 | 36,338 |
|  | P 76,472 | P 467,811 | P 434,251 | P 978,534 |

  - The Audit Team inspected the structure and facilities of the project to make an assessment of the impact of costs and expenses on the operations of NTA. The results were as follows:

  - The building valued at P66.650 million has become idle. Likewise, the roofs were partly damaged, thus providing passage for sunlight and rains which could impair the machineries and equipment;

  - The machineries and equipment amounting to P10.603 million might have become obsolete, hence there is a need for machine testing and appraisal, to reassess their performance and current values;

  - Engaging of security services to protect the plant is unnecessary since it is fully secured with huge perimeter fences. Likewise, the machineries and equipment were non-detachable to the enclosed building that it would be very difficult to disintegrate and snip the equipment without attracting attention from passersby. Continuous incurrence of the said expenses is therefore unwise; and

  - Electricity and supplies expenses were likewise impractical to sustain since no benefit has been derived from the project.

  - Based on the foregoing results of evaluation, the Audit Team opines that government funds were not expended economically, efficiently and effectively, contrary to the provisions of Section 2 of PD No. 1445, hence resulting to wastage of government funds.

  - We recommended that Management:

  - Stop the continuous incurrence of electricity, security services and general services expenses at the AgriPinoy Milling Complex if NTA cannot identify the source of income that can sustain the maintenance                   expenses of the project;

  - Conduct machine testing to reassess the performance of machineries and equipment;

  - Engage the services of a licensed appraiser to determine the current value of the machineries and equipment and be able to assess possible impairment loss; and

  - Formulate a proper action plan on how to manage or utilize the assets of the milling complex with the end in view of reducing the loss and expense of the government.

  - Management informed that during the meeting of the Members of the NTA Governing Board, they have discussed the damage to the roof of the milling complex and the same will be repaired in 2018. The funds for the repair worth P196,464 was transferred on May 30, 2017. An appraisal will be conducted after the repair is completed to come up with the most reasonable cost/rate to offer for the rental of the space either as a warehouse or trading center or for the sale of the property.

  - As a rejoinder, the Audit Team would like to state that if expenses cannot be avoided in the maintenance of the feed milling complex and NTA has not come up with alternative source of income that will sustain the same, the amount of expenditures be at least be minimized. In all instances, cost-benefit analysis shall be employed prior to making decisions to ensure that government resources are not wasted. We further recommended that Management prepare a three to five year- term plan that will lay down the actions to be taken, procedures and requirements, estimated expenses and projected cash flow statement showing the net cash to be generated as a result of choosing an option.

SUMMARY OF AUDIT DISALLOWANCES, CHARGES AND SUSPENSIONS

- Table 12 summarizes the audit disallowances, charges and suspensions in       CY 2017.   The details and status of the unsettled disallowances, charges and suspensions as of December 31, 2017 are presented in Annex C of this Report.

Table 12 – Audit Disallowances, Charges and Suspensions

|  | Beginning balance | Issuances | Settlement | Ending balance |
| --- | --- | --- | --- | --- |
| Disallowances | P 36,184,526 | P - | P 1,685,857 | P 34,498,669 |
| Charges | 60,280 | - | - | 60,280 |
| Suspensions | 400,338,506 | - | 2,864,680 | 397,473,826 |
|  | P 436,583,312 | P - | P 4,550,537 | P 432,032,775 |