PART III - STATUS OF IMPLEMENTATION OF PRIOR YEARS’

AUDIT RECOMMENDATIONS

Out of the 54 audit recommendations embodied in the previous years’ Annual Audit Reports (AARs), 23 were fully implemented, 24 were partially implemented and 7 were not implemented. Details are as follows.

| Observations and Recommendations |  | Actions Taken/Comments |
| --- | --- | --- |
| CY 2016 AAR - The validity of Cash, Receivables, Prepayments, Other Current Assets and Other Assets accounts totaling P395.552 million representing 40.67 per cent of the total balances of dormant accounts of P972.677 million is doubtful and the probability of full recovery is already remote, if not nil, since these accounts have been dormant for more than 10 to 28 years due to: a) undocumented balances carried over from seven defunct tobacco agencies in calendar year (CY) 1987; and b) the inclusion of unsettled loans of farmers/traders/cooperatives since CY 1996, receivables from officers and employees no longer in the service, and unrecovered investment in bonds as the case for recovery has been dismissed by court among others. We reiterated our previous years’ recommendations that Management require: - The Central Office (CO) and Branch Accountants to: a.1 Complete the documentation of dormant accounts to support the request for authority to write off from the COA, in accordance with existing guidelines; a.2 Establish the correct balances of the receivables accounts pertaining to officers and employees who are still connected with the NTA, and enforce immediate settlement of their obligations, otherwise, deduct from whatever cash/benefits due them; and a.3 Analyze the Prepayment and Other Current Assets accounts, and prepare the necessary adjustments in the books to close accounts, if warranted; - The Legal Officer to: b.1 Make representations with LBP Head Office on the possible redemption of the bonds amounting to P28.634 million, and the results of which shall be the basis for succeeding action to be undertaken; and b.2 Exert all legal remedies for the rescission of the Certificates of Award and for the reconveyance of the pertinent lots located in Tuguegarao, Cagayan to the government pursuant to Resolution No. 258-2012 dated April 12, 2012 of the NTA Governing Board, if the awardees and/or the occupants/possessors/successors of the 20 unpaid lots do not agree to settle in full the cost with interest and penalties for the unpaid lots; and - The Branch Managers of Vigan, Batac and Candon to make representations with the DENR for the possible transfer of the reforestation project sites to the local government units so as to preserve the area. - The existence and completeness of the Property, Plant and Equipment (PPE) account with a carrying value of P480.644 million as at December 31, 2016 could not be ascertained due to: a) inability to conduct of physical inventory of immovable assets totaling P443.120 million; b) discrepancy of P151.349 million between property records of P291.771 million and accounting records of P443.120 million; c) non-provision of allowance for impairment of assets in Cagayan Branch Office that remained idle for years; and d) non-maintenance of Property, Plant and Equipment Ledger Cards (PPELCs) and Property Cards (PCs) by the Tobacco Dust Processing Project (TDPP) Accounting and Property Units; thus, reconciliation of accounting records with property records cannot be conducted. We reiterated our prior year’s audit recommendations and Management agreed to: - Create an Inventory Committee at the CO that will be tasked to conduct physical inventory of PPE annually and complete the inventory of immovable assets and prepare the required RPCPPE in conformity with COA Circular No. 80-124 dated January 18, 1980 and Chapter 10, Section 42 of the Government Accounting Manual (GAM), Volume II; - Instruct the Branch Offices’ Managers to create a Committee that will be responsible for the following activities: b.1 Conduct of the complete physical inventory of immovable assets and preparation of the RPCPPE; b.2 Completion of the documentary requirements for the titling of the parcels of land in the name of NTA; and b.3 Consolidation of the TCTs of parcels of land still registered under the name of the defunct PTA, NATOCO and PTRTC including the change of Tax Declarations with the Assessor’s Office of concerned LGUs; - Instruct the Accountants and Property Officers/Custodians of CO and Branches to conduct periodic reconciliation between accounting and property records and adjust affected accounts accordingly; - Require the Branch Manager of NTA-Cagayan Branch to: d.1 Conduct a feasibility study on the idle assets to determine the possibility of generating income therefrom to be utilized for the improvement of said assets; and d.2 Evaluate the current conditions of the idle assets and determine if there are impairment losses in conformity with PPSAS 21, for fair presentation on the financial statements; and - Require the TDPP Accounting Unit and the Plant Supervisor and Property Custodian to maintain and update PPELCs and PCs, respectively, and conduct periodic reconciliation of their records. - Ten Laboratory Equipment, Power Room and Visitors Quarter (Male and Female Dorm) totaling P35.236 million were not insured with the General Insurance Fund (GIF) of the Government Service Insurance System (GSIS); thus, denying NTA adequate and reliable protection against any damage to or loss of the uninsured properties. We recommended and Management agreed to: - Submit an updated inventory of all the insurable properties of NTA duly verified by the Audit Team to the GIF of the GSIS; and - Ensure that all insurable assets and properties of NTA are adequately covered with insurance for protection against damages or losses. - The delayed completion of the 3-floor NTA Quality Assurance Laboratory Building with a contract cost of the P19.647 million due to Contractor’s non-submission of the certification that the materials installed can endure two-hour fire which resulted in the non-issuance of Building Permit by the Quezon City Engineer’s Office, caused the delay in the installation and commissioning of 10 laboratory equipment procured totaling P30.774 million, hence, deprived the intended beneficiaries of the timely benefits that could be deprived from the Capability Enhancement for Quality Assurance Project. We recommended and Management agreed to: - Require the Contractor to immediately comply all the requirements needed in the issuance of the Building Permit by the Quezon City Engineer’s Office to avoid further delay in the completion of the construction of the Quality Assurance Laboratory Building; and - Monitor closely all project activities to avoid incurrence of further delay and impose penalties, if necessary, for the delayed completion of the construction of the building. - The low collection efficiency of only P124.032 million or 35.71 per cent out of the estimated collectibles of P347.305 million in CY 2016 on loans receivable were attributed to financial, technical and other problems of the tobacco farmers, which include, among others: a) proceeds from tobacco sales were not enough to cover amortization or used for other priorities of loan borrowers; b) over exposure of borrowers to various loan programs; and c) damaged crop or poor harvest of tobacco farmers; thus, depriving NTA of the much needed funds in the pursuit of its mandate. We reiterated our previous years’ recommendations that Management: - Limit to viable and sustainable projects those loans to be extended to farmers to ensure collection, consider granting of loans only to those tobacco-farmers in good credit standing, and deduct from the proceeds of a new loan the previous loan balances of farmer-availees to prevent accumulation of arrearages; - Continue to intensify collection efforts by involving all the Branch Managers and Extension Workers to go after the delinquent tobacco farmers; and - File collection suits, if warranted. - In NTA-La Union Branch, the farm inputs specifically fertilizers and pesticides released to the tobacco farmers in the form of loan assistance were not coursed through public bidding, contrary to the pertinent provisions of Republic Act (RA) No. 9184 and its Revised Implementing Rules and Regulations (IRR), thereby deviating from the principle of transparency and accountability in government transactions. We recommended and Management agreed to conduct public bidding in compliance with RA No. 9184 and its Revised IRR in the procurement of farm inputs specifically fertilizers and pesticides instead of releasing the fund in the form of cash to loan-availees. AGRIPINOY TOBACCO FARMERS’ PROCESSING AND TRADING CENTER (NTA AgriPinoy) - Piglet and feed requirements with a total cost of P26.306 million for the Hog Fattening Project were procured from Universal Robina Corporation (URC) without the conduct of competitive bidding, which is not beneficial to the hog growers due to: a) the additional cost of freight of piglets and feeds were passed on to the farmers; b) losses were assumed by hog growers due to the absence of warranty that could have answered for the replacement of piglets that dies within 0-14 days from date of delivery; and c) purchase discount and appropriate tax were not withheld on gross payments; hence, there is no guarantee that the availed price and quality of procured items serve the best interest of both the hog growers and the government. We recommended that Management consider suspending the direct release to hog growers the loan proceeds allocated for the procurement of piglets and feeds; instead, procure the necessary hog production requirements, i.e. piglets and feeds, through competitive bidding to allow various suppliers to participate so as to obtain the most advantageous price for the hog growers and the government. - Losses on spoilage and shrinkage of live hogs and meat products were not recognized during the year as required in PPSAS 12, thus understating Loss by P3.397 million and overstating Raw Materials-Hogs and Finished Goods by P1.899 million and P1.498 million, respectively. We recommended that Management direct the Accountant to make necessary adjustments in the books recognizing the loss on inventory spoilage and shrinkage to fairly present the accounts in the financial statements. Likewise, require the Storekeeper to maintain perpetual records for inventory, for accountability purposes. - The continuous incurrence of losses caused wastage of government funds and threatened the ability of NTA to sustain the operation of the AgriPinoy Project. We reiterated our previous year’s recommendations that Management: - Exert more effort to market the AgriPinoy finished products and hire and designate a qualified/experienced full time Marketing and Sales Head who has the expertise in marketing strategies and promotion campaigns; and - Limit the hiring of JO employees to reduce the administrative selling costs; We likewise recommended that Management: - Make a commitment until end of CY 2017 to attain a break-even point at the minimum, or consider the closure of the operations to cease from incurring further losses and minimize wastage of government funds; and - Henceforth, refrain from investing government funds in capital intensive projects such as AgriPinoy where NTA might not be adequately equipped to run. Instead, focus on providing services that are badly needed by tobacco farmers. TOBACCO DUST PRODUCTION AGRIBUSINESS PROJECT (TDPAP) - Recurring losses of the Tobacco Dust Production Agribusiness Project (TDPAP), which already reached P18.003 million since it started operations in CY 2009 threatened the sustainability and viability of the Project. We recommended that Management: - Conduct an in-depth evaluation of the operations of the Plant to determine whether to continue or stop its operations so as to reduce the incurrence of additional cost and expenses especially the manufacturing overhead costs; and - Develop alternative business proposals for the tobacco dust Plant in the event that its operation will no longer be pursued, such as offer for lease or dispose the Plant so as not to waste government funds and property. Further, we strongly recommended that Management carefully determine the strategies that would be most advantageous to the operations of NTA in the delivery of its services to the tobacco farmers. IRRIGATION SUPPORT PROJECT FOR SMALL TOBACCO FARMERS (ISPSTFs) - Despite not in consonance with its mandate as provided under EO No. 245, the NTA continued to undertake the overall supervision of the implementation of 42 irrigation support projects totaling P257.972 million in CY 2016. In addition, several deficiencies were noted in the implementation of the ISPSTFs which include, among others: a) the continued recording of funds transferred to LGUs totaling P257.972 million as outright expense in the books of NTA, thus, the Agency incurred net loss of P100.264 million in CY 2016; b) the recognition of assets in the books of the appropriate recipient could not be facilitated in the absence of implementing guidelines who would book up the completed irrigation project; c) non-submission of documentary requirements, such as certification of the NTA Accountant that funds released were already liquidated and accounted for in the books, Official Receipts (ORs) to acknowledge receipt of fund/s, and feasibility studies for 29 projects worth P222.354 million prior to execution of contracts to support the validity of transactions contrary to Section 4(6) of PD No. 1445; and d) the unutilized portion of funds totaling P398,354 were not returned to NTA by 11 LGUs contrary to Item 4.9 of COA Circular No. 94-013, while a total of P173.987 million has not yet been released to LGUs due to absence of certificates of acceptance for the completed irrigation projects from the Municipal Mayors and their requests for payment of final fund releases. Meanwhile, funds totaling P26.500 million were not transferred to six LGUS due to non-implementation of the project during the year, thus depriving intended beneficiaries of the benefits that could have been derived from the project. We reiterated our previous year’s recommendation that Management consider the involvement of NIA in the implementation of its on-going irrigation projects under the ISPSTFs particularly in the preparation of the feasibility studies and the preparation of engineering design for new projects considering that NIA has the mandate to plan, design, construct, and/or improve all types of irrigation projects. We also recommended that Management: - Revisit the MOAs and consider inclusion of the following: (i) accounting for fund transfers from source agency to implementing agency in compliance with COA Circular No. 94-013; and (ii) establishing ownership of the projects completed for purposes of recognizing the asset in the respective books of accounts and (iii) donating to appropriate recipients all projects completed so that proper recognition of the completed projects as assets in the books of the recipients will be facilitated; - Direct the Accountant and concerned LGUs to submit all the documentary requirements to support the validity of the transactions in compliance with Section 4(6) of PD No. 1445 to avoid suspension of said transactions in audit; - Require the concerned LGUs to return the utilized portion of funds to NTA in compliance with COA Circular No. 94-013; and - Set/provide time frame to implement the projects to ensure that these are implemented as planned and that intended beneficiaries could timely benefit therefrom. DISASTER RISK REDUCTION AND MANAGEMENT (DRRM) PROGRAM - The P4 million funds for Risk Management Program (RMP) remained unutilized as of December 31, 2016 due to: a) non-submission of Master List of affected tobacco farmers damaged by typhoon; b) Statistical Report of the extensive damages caused by typhoons and flood to tobacco farmers; c) budget was insufficient in allocating the financial assistance equally to numerous affected tobacco farmers; and d) lack of manpower to inspect and prepare the evaluation report on the damaged area; thus, the targeted beneficiaries of the financial assistance who were affected by disasters/calamities such as typhoons, flood, drought and crop infestations/diseases, in the Cordillera Administrative Region (CAR) and Regions I and II were deprived not only of the timely delivery of benefits of the Program, but also protection from natural calamities and disasters. We recommended and Management agreed to: - Strictly follow the applicable provisions of RA No. 10121 in the planning/budgeting of DRRM funds and COA Circular No. 2014-002 dated April 15, 2014; - Prioritize the programs and projects that would be implemented, if calamities may arise, given the limited funds; - Submit the projects and programs listed in the RMP for review and approval by the Board of Directors and the duly approved Board Resolution on the NTA RMP for CY 2016; and - Ensure that the DRRM Fund is fully utilized based on the approved NTA DRRM program/projects. GENDER AND DEVELOPMENT (GAD) - The NTA allotted a total budget f P40.414 million for its GAD Programs, Activities and Projects (PAPs) for CY 2016 in compliance with the Philippine Commission on Women-National Economic and Development Authority-Department of Budget and Management (PCW-NEDA-DBM) Joint Circular No. 2012-01 dated August 22, 2012. Out of the P40.414 million approved GAD budgets, only P34.911 million or 86.38 per cent was spent for GAD activities in CY 2016, thus, depriving the intended beneficiaries of the benefits that could have been deprived from the unimplemented projects and activities. We recommended and Management agreed to: - Fully utilize the fund allocated for GAD and implement programs and projects effectively in accordance with NTA GPB; and - Submit the NTA Annual GPB to PCW for their review, approval and endorsement to the DA, to ensure that the GAD activities are responsive to the identified gender issues and that gender issues are fully addressed during the year. CY 2015 AAR - The proposal for dacion en pago of NTA to the Philippine Deposit Insurance Corporation (PDIC) for the disposable portions of its properties in Rodriguez, Rizal as full equivalent/settlement of its principal loan, interest and penalty charges from the Philippine National Bank (PNB) that were dacioned/transferred by the latter to PDIC in CY 2002 remained unsettled; thus, original loan, interest and penalty of P78.729 million have substantially increased to P282.998 million as at December 31, 2015 due to accumulation of interest and penalty charges of P67.674 million and P136.595 million, respectively. These penalties and charges were not recorded in the books thereby understating the expense and liability accounts by P204.269 million and overstating the retained earnings by the same amount. We recommended that Management make a representation with PDIC for the speedy approval of their proposal for dacion en pago to prevent further accumulation of interest and penalty charges; and - The failure of the Bids and Awards Committee (BAC) to recommend to the Head of the Procuring Entity (HOPE) the awarding of security services to the responsive/compliant bidder after the public bidding conducted in CY 2013, resulted in monthly renewal of security services contract of the service provider whose original contract with NTA expired since CY 2001, in violation of Government Procurement Policy Board (GPPB) Resolution No. 23-2007 dated September 28, 2007 and pertinent provisions of Republic Act No. 9184. We recommended that Management consider awarding to the winning/ compliant and responsive bidder the contract for security services in compliance with the pertinent provisions of RA No. 9184. - The payment of Longevity Pay (LP) to 140 NTA personnel who were on board prior to June 30, 1989 based on their previous years’ monthly rates ranging from P1,050 to P1,450 or a total of P2.076 million exceeded by P1.406 million when compared with the P0.670 million LP in the CY 2015 COB approved by the DBM, hence, could not be allowed in audit. We recommended and Management agreed to instruct the Manager, Administrative Department to pay LP within the approved budget to avoid disallowance in audit. VARIOUS NTA PROJECTS - The RFEFDPREI was not implemented as planned from CYs 2014 to 2015 due to lack of tobacco farmers with suitable/plantable areas and available for the project; hence, the targeted number of loan borrowers/availees were not attained resulting in unutilized funds of P75.193 million as at year-end. Likewise, the survival rates of the Ipil-ipil trees planted in highlands were low ranging from 35 to 80 per cent which might result in non-attainment of the collection target by CY 2017. We recommended that Management: - Instruct the Manager, CPD to revisit the project’s implementing guidelines to consider, among others, the inclusion of actual inspection of proposed project sites and propose amendment(s) on pertinent provisions thereof in order to reach the targeted number of beneficiaries, thereby funds for the purpose would be fully utilized; - Consider extending technical assistance to farmers whose plantable areas are in the highlands so as to increase the survival rate of Ipil-ipil trees and instruct the EWs to closely monitor the projects so as loan availees will be able to pay their obligations within the due date(s); and - Henceforth, see to it that careful planning is undertaken in the conceptualization of projects to be implemented to ensure attainment of the desired objectives. - The objectives of the TFEP was not fully attained considering that of the 890 scholarship grantees (SGs) enrolled from School Years (SYs) 2011-2012 to 2015-2016, 236 or 26.52 per cent were removed from the program mostly due to failure to meet the average grade requirements. Likewise, only 64 or 56.14 per cent were able to graduate in CY 2015 out of the 114 SGs admitted into the program in SY 2011-2012 while the other 48 graduates were enrollees in different SYs. Of the 112 graduates, 59 or 53.15 per cent were employed, 28 are unemployed while NTA has no information on the employment status of the remaining 25 graduates, thus the amount of P2.821 million spent for the SGs who were removed from the program and P0.988 million for the 25 graduates who remain unemployed, or a total of P3.809 million, might be considered a waste of government funds. We recommended that Management closely monitor the remaining 542 SGs to ensure that they can graduate and land a job. - The AgriPinoy Milling Complex with total project cost of P100.918 million expected to operate in CY 2013 remained non-operational in CY 2015 due to delayed completion of the building construction on account of time extension and variation/change orders granted for reasons that could have been avoided had there been adequate planning, thus other activities which include fabrication/erection of steel support and platform, construction of powerhouse and supply/installation of machineries and equipment were also delayed; failure to secure Certificate of Registration for the feed mill operation/product from the Bureau of Animal Industry (BAI); and lack of suppliers of raw materials; thus depriving the intended beneficiaries of the benefits that could have been derived from the project. We recommended that Management: - Carefully plan projects prior to execution in order to avoid/minimize issuance of change/variation/amended orders during the implementation thereof; and - Fast track the completion of the requirements for registration for the feed mill operation/product to facilitate submission to the BAI. |  | This observation was updated and reiterated in Part II – Observation and Recommendation No. 1 of this Report. Partially Implemented. The request for authority to write-off P0.788 million Trade Receivables from Tobacco Centers (TCs) in Region I was granted under COA-NTA Decision No. 2017-01 dated October 26, 2017 and duly recorded under Journal Voucher No. 2248383 dated November 2017. Collection letters were sent in November 2017 to eight TCs with balance amounting to P95,803. Not Implemented. Partially Implemented. The Chief Accountant is in the process of analyzing the dormant Prepayment and Other Current Assets accounts amounting to P4.851 million and P55,620, respectively. Partially Implemented. Certifications on the revocation status of the two corporations where NTA invested funds were released by the Company Registration and Monitoring Department of the Securities and Exchange Commission (SEC) on December 18, 2017. Partially Implemented. Management hired a new Attorney V who will handle pending cases of the Agency. Partially Implemented. Negotiations were established. Awaiting actions on the part of DENR for the permit or authority to cut trees under the supervision of DENR officials. Related observation in Part II - Observation and Recommendation No. 2 of this Report. Fully Implemented. The Inventory Committee already submitted the RPCPPE to the Audit Team on January 31, 2018. Partially Implemented. Physical inventory of immovable assets was conducted by the Provincial Branch Offices of Vigan, Batac, Pangasinan, Isabela, La Union, and the AgriPinoy. Partially Implemented. NTA hired a full-time technical person to assess the property for titling of the parcels of land. Partially Implemented. The hired technical assistant is reviewing all properties and doing the leg work in titling the properties. Partially Implemented. The Accountant and Property Officer of CO already reconciled the accounting and property records for PPEs amounting to P391.956 million. Not Implemented. The Cagayan Branch Manager and staff will be required by the Management to conduct feasibility study. Partially Implemented. A proposed training facility replacing the warehouse will be constructed and, expected construction will commence in 2019. Still not subjected for any impairment losses. Fully Implemented. The reconciliation of PPELCs and PCs was updated. Fully Implemented. The Property Division submitted on October 27, 2017 the inventory of insurable properties of NTA to the GIF of the GSIS. Fully Implemented. Ten Laboratory Equipment and Visitors Quarter were insured from July 14, 2017 to July 14, 2018. Fully Implemented. Copies of the Building Permit and Occupancy Permit were submitted to the Audit Team on August 9, 2017 and November 6, 2017, respectively. Partially Implemented. The liquidated damages shall be deducted from the final payment upon issuance of the final billing. Related discussion in Part II-Observation and Recommendation No. 1 of this Report. Not Implemented. Deduction of the loan balance from the proceeds of a new loan is not feasible because the loan proceed amount was the exact amount needed by a farmer for the tobacco farming season. Partially Implemented. The Branch Managers were instructed by the Board of Directors to strengthen collection efforts. Not Implemented. Branch Managers will review the past due accounts to determine those that will be referred for litigation. Fully Implemented. All production inputs for CY 2017 were done through public bidding. The bidding for the fertilizers, fungicide and desuckercides were undertaken. Fully Implemented. The release of loans, which covered the first quarter of CY 2017, to hog growers has been suspended since April 2017. Fully Implemented. Adjusting entry to take up the spoilage and shrinkage was taken up in March 2017. Fully Implemented. AgriPinoy sold carcass in last quarter of CY 2017. Fully Implemented. Reduced JOs by 50 per cent. Generated savings about P300,000 per month. Fully Implemented. NTA stopped the hog production assistance until the lapses have been controlled. Fully Implemented. NTA initiated an agreement with TESDA for two trainings with the end in view of ensuring income of AgriPinoy of P1 million. This observation was updated and reiterated in Part II – Observation and Recommendation No. 9 of this Report. Not Implemented. Temporarily ceased its production due to the fire which occurred last August 2016. Not Implemented. Partially Implemented. The Branch Manager submitted a proposal to CO to resume TDPAP operation using the tobacco dust machine that was used in Bulacan. It was approved on May 8, 2017 and started to continue its operation. Management renewed their marketing tie up to their biggest distributor to assure sale. This observation was updated and reiterated in Part II – Observation and Recommendation No. 3 of this Report. Partially Implemented. The Administrator and Deputy Administrator for Operations are in the process of coordinating with NIA. Series of meetings held on June 22, 2017, December 7, 2017 and February 6, 2018, were conducted for the issuance of a Joint Agreement between NTA and NIA for the implementation of the Batch IV of the ISPSTF. Partially Implemented. Management is in the process of revising the Guidelines and MOAs. Partially Implemented. Submission of required documents was partially complied. Partially Implemented. Management will prepare collection letters for unutilized funds. During the year, LGU Luba, Abra returned the unutilized portion of the fund transferred amounting to P2,038. Partially Implemented. Fully Implemented. The funds were fully released until the 1st quarter of CY 2017. Fully Implemented. Management prioritized the programs and projects according to their urgency. Fully Implemented. The projects and programs listed in the RMP were submitted for review and approval of the BOD. Partially Implemented. Related observation in Part II - Observation and Recommendation No. 5 of this Report. Fully Implemented. Budget against actual accomplishment report were submitted. Partially Implemented. NTA GPB was submitted to DA, but not endorsed to PCW for review and approval. Partially Implemented. Awaiting decision of the PDIC on the NTA’s letter of proposal dated July 22, 2015 for dacion en pago. Based on PDIC’s reply letter dated August 3, 2015, NTA’s proposal is still being evaluated. Fully Implemented. The NTA conducted public bidding on April 7, 2017 and contract was awarded to the Lowest Calculated Bidder. Fully Implemented. NTA imposed salary deduction from concerned employees’ payroll as refund of their LP received in CY 2015. As of November 2017, LP was fully deducted from their bonus. This observation was updated and reiterated in Part II – Observation and Recommendation No. 8 of this Report. Partially Implemented. Management hired a Certified Forester in CY 2017 to evaluate/study the project. Fully Implemented. Management informed that it is closely monitoring the Program. Fully Implemented. The Board of Directors in CY 2017 temporarily stopped the release of loans to new farmer-beneficiaries until the report of the Certified Forester has been submitted. Fully Implemented. The Scholarship Program was continued until the last batch of scholars have graduated and budget was included in the COB. This observation was updated and reiterated in Part II – Observation and Recommendation No. 10 of this Report. Partially Implemented. Tests on the initial products have been conducted and need further testing/ study. Partially Implemented. In the Board of Directors’ meeting on February 8, 2018, several options were taken up. Management will hire a third party to evaluate the complex. |
| CY 2014 AAR |  |  |
| 23. | Accounts Receivable totaling P1.363 million under the Hog Fattening Program may no longer be collected from the 95 beneficiaries’ due to livestock mortality which was not properly documented, and beneficiaries who are no longer qualified in the second cycle of loan availment due to low production yield, thus, may result in the depletion of funds that could hinder the continuity of the project implementation. We recommended and Management agreed to: - Include in the guidelines as part of the responsibility of the beneficiary to notify NTA immediately in cases of death of hogs’ due to natural calamity or epidemic diseases so that conduct of inspection by the Municipal Veterinarian can be timely requested; and - Instruct the Tobacco Technicians to always secure post mortem report of death of hogs from the Municipal Veterinarian as basis for requesting for write off of the accounts from the Commission on Audit, if warranted. | Fully Implemented. NTA informed that the Guidelines on the hog fattening contract is being reviewed and revised, if necessary. Fully Implemented. |
| CY 2013 AAR |  |  |
| 24. | Accumulated cash shortage in the total amount of P322,049 was established on the cash and accounts of the Collecting Officer covering the period from May 28, 2013 to January 13, 2014, for failure to deposit collections intact to NTA’s authorized government depository bank as required by regulations. We recommended that Management file appropriate charges against the defaulting Accountable Officer (AO) pursuant to Section 217 of the Revised Penal Code of the Philippines. | Not Implemented. The recommendation might no longer be doable considering that the concerned accountable officer died on September 23, 2015. |